LEGENDS

SCPCPL		: S.C. Power Company Pvt. Ltd.

T1HPP		: Tila 1 Hydropower Project

NEA		: Nepal Electricity Authority

PRoR		: Peaking Run of River

PPA		: Power Purchase Agreement

COD		: Commercial Operation Date

RCOD		: Required Commercial Operation Date

DE			: Debt-Equity

IPO		: Initial Public Offerings

SEBON		: Securities Board of Nepal

IEE			: Initial Environmental Examination

DDA		: Due Diligence Appraisal

DPR		: Detailed Project Report

ERT		: Electrical Resistivity Tomography

DHM		: Department of Hydrology & Meteorology

NRB		: Nepal Rastra Bank

RPGCL		: Rastriya Prasaran Grid Company Ltd

PEVC		: Private Equity & Venture Capital

IDC		: Interest During Construction

GOI		: Gross Operating Income

NOI		: Net Operating Income

FCDL		: Foreign Currency Dealing Limit

HSA		: Hydropower Sustainability Alliance

ESG		: Environmental, Social, and Governance

ESDD		: Environmental & Social Due Diligence

E & S		: Environmental & Social

HPP		: Hydropower Project

OHS		: Occupational Health & Safety

K			: Thousand

kW			: Kilo Watt

MW		: Mega Watt

GWh		: Giga Watt Hour

B.S			: Bikram Sambat

TL			: Transmission line

kV			: Kilo Volt

SS			: Sub station

HRT		: Headrace Tunnel

masl		: Meter above sea level

m3/s		: cubic meter per second

RPM		: Revolutions per minute

D/C		: double circuit

S/C		: Single circuit

PROPOSAL:

To seek approval to provide following facilities:

- Term Loan limit of NPR 10,000 million repayable in 17 years (including 5 years' moratorium period) to finance development and construction of the proposed project.

- Bridge Gap Loan (BGL) limit of NPR 5,000 million within the Term Loan limit for bridging financing needs during the project development and construction.

- Cash Credit facility of NPR 600 million, post Commercial Operation Date (COD) to meet the working capital needs against the receivables from NEA.

- Letters of Credit limit of NPR 14,000 million within Consortium Term Loan limit for importing Electromechanical equipment (EM), Hydro mechanical equipment (HM) and other importable items. NMB's share of risk shall be capped at NPR 3,143 million within the Term Loan limit

- Bank Guarantee facility of NPR 500 Million within Term Loan limit to submit various bid/securities for obtaining necessary approval required for project execution and to execute PPA with NEA.

- Allow construction moratorium period for 5 years from the first drawdown date of term loan, allowing drawdown for retentions and pending bills after expiration of the moratorium period.

- Capitalization of interest on the term loan

We propose to capitalize interest during the grace/moratorium period until cash inflows begin from project operations/production.

NRB's Unified Directives 2082, Clause (2), Sub-clause 45 (5), interest capitalized during the moratorium period must be separately transferred to a regulatory reserve as an Interest Capitalized Term Loan (ICTL) for loans approved or with a financial closure date on or after 2079/10/26 B.S. (February 9, 2023 A.D.). However, the Nepal Rastra Bank has directed that banks and financial institutions should formulate and implement separate procedures regarding interest capitalization.

For hydropower projects, solar power and other renewable energy projects, if 60% of the construction work is proven completed, the amount in ICTL can be deducted from the Interest Capitalized Reserve (ICR) and transferred to the retained earnings.

SUMMARIZED EXPOSURE								NPR 000

| PARTICULARS | CURRENT | PROPOSED | O/S |  |
| --- | --- | --- | --- | --- |
| FUNDS-BASED | - | 10,600,000 | - |  |
| NON-FUNDS BASED (LC) | - | (3,143,000) | - |  |
| NON-FUNDS BASED (BG) |  | (500,000) |  |  |
| TOTAL |  | 10,600,000 |  |  |
| EXCEPTION TO SOL |  |  |  |  |
| NET | - | 10,600,000 | - |  |
| OTHER (FCDL) |  | 251,440 |  |  |
| #### TOTAL GROUP LIMIT |  |  |  |  |

Note: A maximum LC limit of NPR 14,000 million shall be booked being the Lead and that shall be shared proportionately among consortium members.

PROJECT INFORMATION

- Project Name: Tila-1 Hydropower Project

- Capacity & Location – 440 MW (as per generation license), 298.75 MW (as per PPA) encompassing Kalika Rural Municipality, Mahabu Rural Municipality, Khanda Chakra Municipality – Kalikot District, Karnali Province, Nepal

- Annual Energy (as per PPA): 1,790.347 GWh [Dry – 600.553 GWh (33.54%) and Wet – 1,189.792 GWh (66.46%)]

- PPA Tariff Rates: Dry Peak - NPR 10.55; Dry Off–Peak - NPR 8.40; Wet - NPR 4.80 per unit during 1st year (6 months dry and 6 months wet season)

- Delivery Point as per PPA: NEA’s Chhinchu (Surkhet) Substation through 400 kV double circuit, approx 80 km from the powerhouse.

- Delivery Point as per MoU with RPGCL: NEA’s Phukot HUB substation (440 kV) through 400 kV double circuit, approx. 6 km from the powerhouse

- EIA approved date: 14/11/2014 A.D. (30/07/2071 B.S.)

- PPA with NEA date: 23/10/2024 A.D (7/07/2081 B.S)

- RCOD: 31/12/2030 A.D. (15/09/2087 B.S) (as per PPA)

T1HPP is a 6-hr peaking run-of-river (PROR) type hydropower project. As per the Generation License, it has an installed capacity of 440 MW with 101.76 m3/s design discharge and 503.53 m gross head. As the signed PPA, the project is for an installed capacity of 298.75 MW. The Developer has planned for having all the Civil and other structures compatible for 440 MW capacity and install the generating equipment only for the PPA capacity at initial stage. It has been planned to evacuate the generated energy into the under-construction Phukot HUB sub-station of Rastriya Prasaran Grid Company Ltd (RPGCL), which is part of the Karnali Corridor Transmission Line. The project will construct about 6 km of 220 kV transmission line for the power evacuation.

T1HPP is located in Kalikot District, Karnali Province. The project structures lies along right bank of Tila river and inside Khandachakra Municipality. Left bank of the river, where the project’s main dam is located, is Mahabu Rural Municipality. The headworks site lies just downstream of the confluence of Tila river and Ruru-Banchu Khola. The powerhouse site lies at about 3 km upstream of the confluence of Tila and Karnali rivers. Geographically, the project has license coordinates of latitudes 29°06'00" & 29°08'40" N and longitudes 81°35'00" & 81°44'38" E. The project received generation license (validity: 2075-05-08 BS to 2110-05-07 BS) on 2075-05-15 BS.

While travelling from Surkhet, the powerhouse site is on the way to Manma bazaar after crossing Tila river by a motorable bridge. Manma is the district headquarter of Kalikot district and the main bazaar lies about 10 km uphill from the powerhouse site.

There are couple of alternatives to reach the project site from Surkhet. One could entirely follow Karnali Highway from Surkhet or go towards Dailekh and then follow Karnali Highway on later stretch. The first site visit team from Banks and FIs (details below) travelled by vehicle from Surkhet and traversed Surkhet-Dailekh road, Siyakot - Lower Dungeswor road and Karnali Highway to reach the project site. With this alternative, total distance upto the powerhouse site is about 135 km.

The first site visit team returned travelling via Karnali Highway, Sai Khola – Chupra road (section of Mid-Hill Highway) and Surkhet – Dailekh road to reach Surkhet. With this alternative, total distance from the powerhouse site is about 175 km.

If flight is available to Jumla, the headworks could also be reached travelling along Karnali Highway (towards Manma) for about 60 km.

Distance between the powerhouse and headworks locations is about 35 km along Karnali Highway (via Manma Bazaar and towards Jumla).

Note: An MoU has been signed with Rastriya Prasaran Grid Company Ltd. (RPGCL) to change the connection point of the PPA  from Chinchu (Surkhet) Hub substation to RPGCL's Phukot Hub Substation on the Karnali Corridor Transmission Line (currently under construction). RPGCL is constructing  Phukot (Kalikot) - Betan (Surkhet) - Dododhara (Kailali) 400 kV D/C transmission line and associated substations. This line is intended to tap 4,000 MW capacity generated from hydropower projects in Karnali Basin to the National Grid. The Project encompasses development of three 400/132 kV substations at Phukot, Betan and Dododhara. RPGCL has already awarded contract to Kalpataru Power Transmission Limited, Gujarat India for the works and the contractor is currently working at the sites. This line is planned to become one of Nepal's major export corridors for electricity to India through Bareily (India).

RPGCL anticipates completing the project (TL) by FY 2088/99 B.S., which aligns with the completion timeline of this Tila 1 HPP. This largely ensures that no evacuation issues will arise for the project after the commercial operation. Current status of the Phukot substation is as under:

- Land acquisition largely completed

- Detailed engineering completed

- Construction package award completed

- Construction activities have started

Technical Highlights:

Salient features of the project are as under:

River:				 		Tila (Tributary of Karnali)

Type of Project:		 		Peaking Run-of-River

Dam Location:			 		downstream of Tila–Ruru Confluence

Latitude (Dam):		 		29°06’ 00” N

Longitude (Dam):		 		81°44’38” E

Powerhouse, Location:	 		Underground, upstream of Serighat Village on right bank

Latitude (Powerhouse):	 		29°10’ 00” N

Longitude (Powerhouse):	 		81°52’ 00” E

Hydrology

River Basin:			 		Karnali

Catchment Area of Source River at intake:	 3,355 km2

Rain-fed Area:					 3,080 km2

Snow-fed Area:				 275 km2 (assuming permanent snow line at El. 4,500 m)

Annual Average Rainfall:			 1,082 mm

Annual Average Runoff Yield:		 803 mm

Probable Maximum Flood (PMF):		 13,821 cumecs

Diversion Discharge:				 660 cumecs (1-in-10-year flood)

Reservoir

Full Reservoir Level (FRL):			 1,295 m

Minimum Draw Down Level (MDDL):		 1,275 m

Gross Storage:				 2.3 MCM

Live Storage:					 1.7 MCM

Surface Area at FRL:				 11.6 ha

Length of Reservoir:				 895 m

Dam

Type:						 Concrete Gravity Dam

Dam Top Level:				 1,298 m

River Bed Level:				 1,243 m

Length of Dam Top:				 182.4 m

Diversion Facilities

Length:					 462 m, D-shaped tunnel

Diameter / Cross-section:			 7.6 m, pressure flow

Diversion Flow:				 660 cumecs (1-in-10-year flood)

Spillway

Type:						 Gated Ogee type

Number of Gates:				 7

Size and Type of Gate:			 7.7 m × 13.5 m radial gates with breast wall

Crest Elevation:				 1,255 m

Bucket Type:					 Trajectory type bucket

Invert Elevation of Bucket:			 1,243 m

Lip Level of Bucket:				 1,247.69 m

Power Intake

Design Discharge:				 122.12 cumecs (with 20% flushing discharge)

Number and Size of Openings:		 2

Invert Level of Intake:				 1,265.5 m

Trash Rack:					 Inclined at 10° with vertical

Feeder Tunnel

Shape and Size:				 D-shaped, 4.40 m diameter

Number of Feeder Tunnels:			 2

Length of Tunnel 1:				 195.5 m

Length of Tunnel 2:				 153.5 m

Desilting Chamber

Number:					 2

Size and Shape:				 12 m × 18.8 m × 290 m, Dufour shaped

Particle Size to be Excluded:			 Coarser than 0.20 mm

Silt Flushing Tunnel

Number of Tunnels:				 2

Size and Shape:				 1.5 m × 2.7 m, modified D-shaped (free flow)

Length of Tunnel 1:				 42 m

Length of Tunnel 2:				 77 m

Head Race Tunnel

Shape and Size:				 Modified horseshoe, 6 m dia., concrete lined

Design Discharge:				 101.76 cumecs

Length of Tunnel:				 13,770 m

Number of Adits:				 6

Size and Shape of Adits:			 5 m × 6 m, modified D-shaped

Surge Shaft

Type:						 Open to sky, restricted orifice

Size and Shape:				 10 m dia., circular

Height of Surge Shaft:			 128 m

Upsurge Level:				 1,348 m

Down Surge Level:				 1,227.5 m

Top Level of Surge Shaft:			 1,350 m

Bottom Level of Surge Shaft:			 1,222 m

Orifice Diameter:				 2.4 m

Pressure Shaft

Main Pressure Shaft:				3.25 m dia., circular

Number of Pressure Shafts:			 2 (steel lined)

Length of Pressure Shaft 1:			 846 m

Length of Pressure Shaft 2:			 816 m

Branch Pressure Shaft: 			2.5 m dia., circular

Number of Penstocks:			 4

Length of Penstocks:				 43 m, 38 m, 56 m, 50 m

Powerhouse

Type:						 Underground

Generator Floor Level:			 778.5 m

Turbine Floor Level:				 774.0 m

Service Bay Floor Level:			 783.5 m

Machine Hall Size (for 1 unit):		 18.5 m × 69.5 m

Transformer Hall Size:			 16 m × 121.9 m

Turbine

Type:						 Pelton

Number:					 4

Gross Head:					 510.5 m (corresponding to Normal Tail Water Level)

Discharge per Unit:				 17.7 m3/s

Rated Output Capacity per Unit:		 75 MW

Efficiency:					 92%

Governor

Type:						 Electronic with PID control

Adjustment for Speed Drop:			 Between 0 and 5%

Generator

Type:						 Synchronous, 3-phase, salient pole

Rated Output Capacity per Unit:		 88.23 MVA

Power Factor:					 0.85

Voltage:					 11 kV

Frequency:					 50 Hz

Number of Units:				 4

Excitation System:				 Brushless

Efficiency:					 97%

Transformer

Type:						 Single phase, ONAN, outdoor, 50 Hz

Rated Capacity:				 29.5 MVA

Voltage Ratio:					 11 kV / 400 kV

Frequency:					 50 Hz

Number of Units:				 13

Efficiency:					 99%

Tail Race Tunnel

Tail Race Tunnel Length:			 642 m

Tail Race Tunnel Size:			 80 m × 30 m

Transmission Line

Type:						 440 kV Double Circuit

Length:					 6 km

Delivery Point:					 440 kV Pukhot Substation

Access

Kathmandu – Nepalgunj		:	519 Km

Nepalgunj – Surkhet			:	110 Km

Surkhet - Manma			:	150 Km

Manma - Dam Site (Headworks)	: 	20 Km

Project Design Philosophy and conceptualization in the DPR:

Project Hydrology:

Tila River is a significant river in Nepal, known for its hydropower potential. Rivers in this region are snowfed perennial in nature and have huge hydro potential. Catchment of T1 HPP lies in Karnali river basin and is a sub-catchment of the Karnali basin. The catchment area at the dam site is 3,355 sq. km. With about 7% of the catchment lying above permanent snow-covered area, about 93% of the catchment area is rain-fed. The basin hydrology is governed by annual rainfall, the form of precipitation (rain or snow), their variability in time and space, and the response of the basin to them. Total length of Tila River up to the project diversion site is approximately 107 km. The river bed elevation at the dam site is 1,242 m. The important streams joining Tila River are Sinja Khola and Ruru Banchu Khola, which are also perennial in nature. The flow estimation, design discharge determination, flood analysis and sediment assessment are all conducted during the DPR.

There are three river gauge stations of DHM in the Tila River Basin; they are: Station (Stn.) No. 220 at Nagma in Tila River, Stn. No. 230 at Sereghat in Tila River and Stn. No. 225 at Diware in Sinja Khola. Sinja Khola is a major tributary of Tila River, upstream of this projects dam. Long term available data of these stations have been considered during the DPR for estimating the monthly flow availability for Tila1 HPP. During the Detail Engineering, the latest available data from these stations will also be used, on top of the data during the DPR, to refine the estimated hydrology and prepare for a prompt and accurate availability declaration after commercial operation of the project.

Geology and Geotechnical Investigations and status

During the DPR, extensive geological and geotechnical investigations are included, comprising:

• Regional geological studies

• Detailed geological mapping

• Geomorphological assessment

• Alternative site investigations

• Exploratory drilling

• Exploratory drifting

• In-situ testing

• Laboratory testing

• Seismic hazard assessment

The investigations covered all major project components including Diversion structure, Intake. Underground desilting chambers, Headrace tunnel, Surge shaft, Pressure shafts, Underground powerhouse, Tailrace structures, etc.

The project area lies within the Higher Himalayan geological zone and predominantly comprises Gneiss, Schist, Banded gneiss and Augen gneiss. The DPR identifies the project area as being located within competent metamorphic rock formations associated with the Kalikot Formation and Sallyanigad Formation. The geological investigations indicate that majority of the project alignment passes through competent rock masses suitable for underground excavation works.

The DPR includes extensive subsurface investigations including:

• 11 exploratory drill holes

• Multiple exploratory drifts

• Detailed geological mapping

• Permeability testing

• Rock mass characterization

• Test tunnel at powerhouse location

• Two test tunnels at headworks location

The investigations confirm the presence of generally favorable foundation conditions for the diversion structure and underground works. Potential localized shear zones and fractured rock zones identified in the DPR are typical of Himalayan hydropower projects and have been appropriately considered in the original design.

Headrace Tunnel: The DPR envisages an approximately 13.77 km long headrace tunnel passing through

predominantly gneissic formations. The geological assessment concludes that tunneling conditions are expected to be generally good to fair, with isolated weak zones requiring localized support measures.

Underground Powerhouse: The proposed underground powerhouse cavern and associated tunnels are located in competent gneissic rock masses. The geological investigations and stability assessments carried out during DPR preparation is technically acceptable for implementation.

Seismic Assessment: The DPR includes a deterministic seismic hazard assessment and review of historical seismicity. The methodology adopted is consistent with accepted engineering practices. However, seismic parameters should be updated during detailed engineering in accordance with prevailing national and international design standards.

Based on the review of available geological and geotechnical data, it could be concluded that:

• The investigations conducted during DPR preparation are comprehensive.

• Geological conditions remain favorable for project implementation.

• No major geological constraints have been identified that would warrant revision of the project layout.

• Existing locations of the diversion structure, tunnel alignment, surge facilities, and powerhouse are technically suitable.

• Additional confirmatory investigations may be undertaken during detailed design and construction stages, but no fundamental revision of the DPR is required.

Civil Engineering Structures

1. Diversion Dam and Spillway

For the proposed concrete diversion dam, spillway arrangement, energy dissipation system,

auxiliary spillway and associated hydraulic structures, the DPR adopted:

• Gated overflow spillway

• Flip bucket energy dissipation arrangement

• Auxiliary chute spillway for debris passage

• Comprehensive foundation treatment measures

• Detailed drainage and instrumentation systems

The spillway configuration was developed after evaluation of hydraulic performance and downstream river conditions. The selected flip bucket arrangement is considered due to the low tailwater levels and high flood discharge intensity anticipated at the site. Detailed stability analyses were also checked for all loading combinations including:

• Construction condition.

• Normal operating condition.

• Flood condition.

• Design Basis Earthquake (DBE).

• Maximum Credible Earthquake (MCE).

• Full uplift condition.

The DPR analyses demonstrated satisfactory factors of safety against sliding, overturning, and

excessive stresses under all design scenarios.

2. Foundation Treatment and Dam Safety:

The DPR proposes comprehensive foundation treatment measures including:

• Consolidation grouting

• Curtain grouting

• Drainage galleries

• Foundation drainage holes

• Internal drainage systems

• Water stops and contraction joints

• Dam instrumentation systems

The proposed arrangements are consistent with accepted international practices for concrete diversion structures founded on Himalayan rock formations. The instrumentation system proposed in the DPR provides adequate monitoring capability for:

• Seepage

• Uplift pressures

• Structural deformation

• Joint movement

• Piezometric conditions

• Seismic response

3. River Diversion Works

The temporary river diversion scheme comprises:

• Diversion tunnel.

• Upstream cofferdam.

• Downstream cofferdam.

• Construction dykes.

• River closure arrangements.

The diversion system is designed for a 1-in-10-year return period diversion flood in accordance with prevailing Nepalese hydropower design practices. During detailed engineering and construction planning, the diversion flood may be reassessed using updated hydrological records available since the DPR.

4, Intake Structure

The intake arrangement is located adjacent to the diversion structure on the right bank. The design incorporates:

• Four intake bays

• Bell-mouth intake configuration

• Trash rack system

• Intake gates and bulkhead gates

• Feeder tunnels connecting to desilting chambers

The intake orientation and hydraulic configuration are thus selected to optimize flow conditions while minimizing sediment ingress and vortex formation. Geological conditions at the intake site are favorable with competent gneissic bedrock exposed near the foundation level.

5. Desilting Chambers

The DPR proposes two underground desilting chambers designed to remove sediment particles greater than 0.20 mm before entering the water conductor system. The design incorporates:

• Twin desilting chambers

• Flushing arrangements

• Maintenance access galleries

• Sediment evacuation systems

• Rock support systems

• Concrete lining and drainage provisions

The dual-chamber configuration provides operational flexibility and improved reliability.

6. Headrace Tunnel

The proposed water conveyance system comprises a 13.77 km long concrete-lined headrace tunnel.

The DPR includes optimization studies evaluating various tunnel diameters and configurations. Based on economic and hydraulic analysis, a 6.0 m diameter modified horseshoe tunnel was selected as the optimum solution. The design velocity remains within accepted limits for concrete-lined pressure tunnels.

Geological investigations indicate that majority of the tunnel alignment passes through fair to good quality rock masses, with localized weaker zones requiring support. The DPR includes comprehensive support recommendations for all anticipated rock classes including:

• Shotcrete support

• Rock bolting

• Steel ribs

• Fore poling arrangements

• Concrete lining

7. Surge Shaft

The need for a surge shaft was evaluated in the DPR using accepted hydraulic criteria including:

• L/H ratio

• Acceleration time analysis

• Transient surge analysis

• Thoma stability criteria

These investigations demonstrated the necessity of a surge shaft due to the substantial length of the water conductor system and the high operating head. The selected surge shaft configuration provides adequate hydraulic stability and protection against water hammer effects.

8. Underground Structures

The underground structures, including Desilting caverns, Headrace tunnel, Surge shaft, Pressure shaft system, Powerhouse cavern, etc were developed based on detailed geological investigations and rock mass assessments. The selected locations utilize competent rock masses and are consistent with accepted underground hydropower design practices.

However, considering the load-carrying capacity of bridges on the access route, the number of turbines and transformers, consequently the size of the powerhouse, may change during the detail engineering.

The necessitated modifications in the electromechanical configuration will require reassessment and optimization of the underground powerhouse complex, including:

• Machine hall dimensions.

• Unit spacing and arrangement.

• Erection bay requirements.

• Crane capacity and operational clearances.

• Transformer cavern and auxiliary facilities.

• Cable galleries and service tunnels.

• Ventilation and access arrangements.

Accordingly, while the geological suitability and general location of the underground structures remain competent, the underground powerhouse cavern and associated electromechanical spaces shall be re-optimized to accommodate the revised generating unit configuration.

9. Hydromechanical Components

Hydraulic calculations for waterways, tunnels, pressure shafts, and associated structures have been conducted during the DPR.

10. Electromechanical Equipment

The DPR considered installation of 4 units of 110 MW generators. Based on transportation and infrastructure assumptions, it is now observed that transportation of very large generator components to the project site may present significant logistical challenges. Therefore, it is now under discussion and planning that:

• 4 generating units be installed, along with 13 transformers including one spare.

• Individual unit ratings be optimized to suit transportation limitations.

• Modular transportation and erection considerations be incorporated into equipment design.

This modification will improve constructability, reduce transportation risks, and facilitate maintenance activities during operation. Electromechanical equipment shall be installed initially for 298.75 MW, corresponding to the available PPA allocation. That is, 4 units of generators and 13 transformers could be planned initially. This approach will preserve future expansion capability, avoid costly retrofitting of the civil structures, optimize initial capital investment and facilitate future capacity enhancement when additional market opportunities become available.

In addition, the DPR proposes Francis turbines. However, based on a review of project head, discharge characteristics, operational flexibility requirements and current industry practices, it is recommended that the electromechanical design will get revised to adopt Pelton turbines. Advantages include:

• Improved suitability for high-head applications

• Better operational flexibility under variable flow conditions

• Reduced cavitation risk

• Improved efficiency over a wider operating range

• Easier transportation and assembly of runner components in remote locations

Approvals/ Compliances status of the Project

- PPA for 298.75 MW with NEA was executed on 23/10/2024 A.D (2081/7/7 B.S)

- Generation License for 440 MW obtained on 24/8/2018 (2075/5/8 B.S)

- Detailed project report for 298.75 MW capacity prepared on 2012 A.D by SNC Lavalin Engineering India.

- An agreement has been recently signed with Shah Consult International P Ltd (Nepal) for a Due Diligence Study of the project

- EIA for 440 MW capacity was approved on 14/11/2014 A.D. (2071/7/30 B.S.)

- A MoU with RPGCL has been recently signed to connect into Phukot Hub Substation on the Karnali Corridor for the power evacuation.

Site Visits from Banks and FIs:

| First Site Visit Date | 9th-11th July 2026 (25-27 Ashadh 2083 B.S.) |
| --- | --- |
| Representative from NMB Bank | Mr. Sushant Adhikari (Manager Hydro – Project Due Diligence & Guidance and Monitoring & Control) Mr. Bishal Bhattarai (Officer- Environment & Social Risk) |
| Representative from Prabhu Bank Ltd. | Mr. Prem Prasad Dhamala (Relationship Manager) |
| Representative from NIC Asia Bank Ltd. | Mr. Anush Raj Upadhayay (Relationship Manager) |
| Representative from Employees Provident Fund (EPF) | Mr. Shiva Raj Poudel (Senior Manager) |
| Representative from S.C. Power Co. Pvt. Ltd. | Mr. Roshan Shah (Project Director) Mr. Milan Khatiwada (Admin & Account Officer) |
| Second Site Visit Date | 20 -22 July 2026 AD (4 – 6 Srawan 2083 BS) |
| Representative from NMB Bank | Mr. Shiva Raj Pudasaini (Officer- Environment & Social Risk) |
| Representative from Shangri-la Development Bank Ltd. | Mr. Sulav Joshi (Chief Risk Officer) Mr. Sushan Maharjhan |
| Representative from Muktinath Bikas Bank Ltd. | Mr. Umesh Joshi (Head Transformation Officer – Kohalpur) |
| Representative from S.C. Power Co. Pvt. Ltd. | Mr. Roshan Shah (Project Director) Mr. Milan Khatiwada (Admin & Account Officer) |

Mr. Krishna Kumal (Local Consultant - Hydropower Sustainability Alliance) has also carried out site visit from 20 – 22 July, 2026.

Observation of the filed visit

- The section of Karnali Highway traversed by the visit team is in poor condition with narrow width, sharp bends, and limited blacktopped stretches. However, the highway condition improves after crossing Tila river up to the headworks, with wider and mostly blacktopped sections. The highway is known for rockfall hazards, especially during rainy seasons, which were observed by the team. Roads such as Surkhet–Dailekh and parts of the Mid-Hill Highway are in good condition, mostly newly blacktopped with light traffic.

- Transporting construction materials via Karnali Highway will be challenging, requiring regular maintenance and upgrades for smoother vehicle movement.

- One earthen road (Sere – Pantadi) starting from Serighat (located just before Tila river crossing along Karnali Highway) runs along left bank of Tila river and connects to the headworks area (Pantadi). The road is said to be about 17 km long and was excavated/ constructed few years back. Alignment of this road seems good with fewer bends and stable geology. Availability of this road is a major advantage for this size project and for a project with headrace tunnel itself being about 14 km. Travelling distance from the powerhouse to the headworks (17 km) will get reduced by half compared to the main access road (37 km) if this Sere – Pandadi access is opened. Gradient of Tila river at the project corridor is steep and drains primarily towards East to West direction.

- The Developer informed that a River gauging station was established in Tila river, close to the headworks area, and the readings had been recorded for couple of years. At present, no such river gauge has been established by the Developer at the project site. A DHM’s river gauge station (Stn no. 230, Serighat) was noticed on right bank of Tila river. Location of this station is close to the tailrace outlet of this project.

- Couple of test tunnels were excavated at the prominent project structures during the time of the Detailed Project Study by SNC Lavalin. Two of these tunnels are present on opposite banks at the headworks location. One of these tunnels, located on the left bank, is also intended to be used as diversion tunnel during construction of the main dam.

- One more test tunnel was excavated at the powerhouse cavern’s construction Adit area. Length of this tunnel is about 180 m and the encountered geology is very stable. No support whatsoever is noticed throughout this tunnel alignment.

- Rock type noticed in the project area mainly are massive blocks of Quartzite, especially at steep cliffs along banks of Tila river and along Karnali Highway. No significant slope stability problem was noticed in the project area and there seems less possibility of landslide during and after the project construction, as the rocks are massive and thick. Overall geology of the project area is good.

- Location of the main dam is at a relatively narrow area with suitable features like space in-and-around and rock condition favorable for the structure.

- A suspension bridge located upstream of the main dam, to cross Tila river, need to be relocated to higher altitude. Also, to be relocated/ shifted uphill, for about 500 m stretch, is Karnali Highway which lies within the reservoir level of this project.

- Location of the intake/ connecting tunnel is downhill of Karnali Highway and will not cause direct disturbance to the Highway during their construction.

- Access roads, all starting from Karnali Highway, toward all of the headrace tunnel Adit portals are still to be constructed. Topography and geological conditions along these proposed access roads towards the Adit portals seem stable and good. In total, about 20 km of internal access roads are to be constructed by the project to reach all the working fronts and structures of the project.

- Mostly steep slopes are observed on surface where the headrace tunnel alignment runs. Moderately weathered rock of massive nature is present along most of the alignment. The rocks are rough and most of the surface openings are of small size.

- Location of the surge shaft top-opening is at a steep area and hence heavy excavation is expected. The location lies at a hilltop. Access road need to be constructed for the surge shaft area.

- The selected location of the underground powerhouse is on right bank of Tila river. Location of the powerhouse’s cavern construction Adit portal is about 250 m from Karnali Highway. During the test tunnel excavation at this location, an access road has been constructed for this 250 m stretch; which currently is not in condition for vehicular movement. About a kilometer of an access road need to be constructed from Karnali Highway upto the main access tunnel of the powerhouse.

- No route survey for the proposed transmission line of the project, connecting into Phukot HUB substation, has been conducted yet.

- Availability of sufficient and suitable space for the permanent camps at the powerhouse location is limited. The Developer is finalising one area, uphill of the powerhouse location, for constructing the camp, which is a logical choice. Couple of other camps also need to be constructed at several locations, like, headworks, headrace tunnel Adit portals, surge shaft, etc. for smoother and speedy construction.

- Except for couple of “solar lift-irrigations” around the powerhouse area, no water sharing issues seem to exist with regards to irrigation and drinking in the project corridor. Water availability to these lift-irrigations also should not be of any concern as the project will be releasing ecological flow during operation and there also are tributaries downstream of the main dam for sustained waterflow in Tila river dewatered zone.

- A 33 kV line (from Manma to Jumla) of NEA is running close to Karnali Highway, which is also close to the construction Adit portals of the headrace tunnel and the other major structures. Hence, the project could use this line for the construction power. Or else, construction power could also be directly tapped from the 33 kV Manma sub-station. During the full construction mobilization, suitable numbers of standby diesel-generators seem to be the prime option for supplying the required quality and quantity construction power.

- Tila river seems to have only little amount of sand deposits of required quality at the project corridor. The riverbed materials are of mixed type mainly with cobble and gravel but with sufficient quantities. Procurement of adequate quality construction materials, especially sand, might also have to be made from a distant location. Muck from all the excavation works of the project also could be used for the construction materials production. Locations of the crusher plants have not yet been finalized; there could be multiple such plants as there will be multiple working fronts.

Suggestions after the site visits are as follows:

The following are the suggestions and conclusions after the field visit:

- Looking at the location and alignment of the project, and also availability of access, the project is in ready to go position for the construction.

- Upgrading of the Sere – Pantadi road should be started immediately. The under-construction bridge at Pantadi (just downstream of the dam’s location) to cross Tila river most likely has to be relocated to nearby location for it to not interfere with the project structures like the main dam and inlet/ connecting tunnels. An access road from this bridge to connect into Karnali Highway also need to be constructed.

- There are multiple works that need to be, or could be, started immediately for the project construction. Works like construction of camps at different locations, construction of access roads towards all the tunnel Adit portals and construction Adits, identification of lands for the crushers and batching plants, procurement of all the private lands, construction power lines, etc should be started soon.

- A detailed survey, including load bearing capacities of the existing bridges along the way, need to be conducted for adequacy and upgrading works required to be done to smoothly transport heavy loads, especially the electromechanical equipment, along Karnali Highway.

- Physical modelling of the headworks, especially the dam and reservoir, is highly preferred for this project which has relatively high gross head.

- Option should also be studied to avoid at initial stage the Adit 4, or Adit 3, of the headrace tunnel. Locations of these Adits are closer to each other and based on the project progress, additional Adit could be constructed during later stage. There also could be an option of having at least one of the Adit portals, likely Adit 2, at the Highway itself.

- It would be better to discuss with the nearby hydropower projects for any possibility of sharing the transmission line upto Phukot HUB sub-station.

- Final coordination between this and Tila-II HEP should be done for finalizing location of the tailrace outlet of Tila-II HEP and location of the main dam of this project.

- Efforts should be made to regularize the Suntharali/ Kotbada Airport of Kalikot. There are many hydropower projects under-development in and around this airport and hence movement of people in the area will sure to get increased exponentially in coming years. Having a reliable and shorter access towards the project will greatly support many critical moments throughout the construction and operation periods. The airport is about 1.5 hrs drive from the powerhouse area and there seems to be a plan of the local government to connect Manma with this airport by a “cableway” which will limit the travel time within minutes.

Attractive Features of the Project

- Availability of long-term hydrological data of the source (Tila) river: Data has been received from Department of Hydrology and Meteorology’s (DHM) gauging stations located upstream and downstream from the project site. These increase level of confidence in the hydrological estimations for the project.

- The source of river is perennial having about 7% of the catchment area (up to the project’s intake) above 5000 masl (permanent snow contribution) and rest of the catchment mostly covered with barren lands and forest with no major human settlement and development. This helps deliver consistent and reliable flow.

- Studies and in-field investigations conducted so far suggest robust geological features at most of the project components’ areas. Sub-surface geological investigations with test tunnels, at prominent project components’ locations, have been done; so do the hydrological and sediment measurements of the source river.

- As the project area is beside a National Highway (Karnali Rajmarg, Surkhet - Jumla), accessibility towards the project is easier and reliable. The project only needs to construct feeder roads towards the project components. Karnali Highway passes close to the powerhouse and headworks area of this project.

- The project’s 1st year’s annual revenue of about 3.82 crore/MW (installed capacity as per the PPA (298.75 MW) and not including reserve margin for 5 wet months), is good even for a 6:6 months PPA type PROR project.

- With a higher gross head, the project’s civil components are comparatively smaller for a project of this size.

- Transmission line from the project to the proposed interconnection point of NEA is only about 6 km long; which is very short for a project of this size. Further, this line could be planned to be constructed jointly by this and upstream Tila-II HEP (420 MW installed capacity).

- Based on the recent developments in cross-border trading of electricity, it is very likely that the project could achieve a competent PPA with an Indian or other party for the remaining capacity (capacity above the current 298.75 MW PPA capacity; i:e: 141.25 MW) even before the COD of 298.75 MW. This PPA for the remaining capacity will sure to further improve financial parameters of the project.

- Quality of the Detail Project study (DPR) is of international standard and competent. The Consultant, SNC Lavalin, is one of the most recognized design consultant in the world for hydropower design and optimization.

Work Schedule:

The tentative work schedule provided by the developer is as follows:

| Particulars | Tentative Completion Date |
| --- | --- |
| Preparatory Works |  |
| Access Road, Camps and Construction Power | Nov-2026 |
| Upstream & Downstream Coffer Dam | May-2027 |
| Diversion Tunnel | May-2027 |
| Civil Construction (Underground Works) |  |
| Headrace Tunnel with Adits, Intake, Desander, Link tunnels. | Jun-2030 |
| Surge Shaft | Sep-2028 |
| Penstock Shaft | Jul-2029 |
| Powerhouse with Adits, Tailrace, Access tunnels. | Dec-2029 |
| Civil Construction (Surface Works) |  |
| Dam | Sep-2030 |
| River Training and Protection Works | Dec-2030 |
| Hydro Mechanical Works | Nov-2030 |
| Electro Mechanical Works | Oct-2030 |
| Transmission Line and Grid Interconnection | Dec-2029 |
| Commercial Operation Date (COD) | Dec-2030 |

Project Cost

Total estimated project (298.75 MW) cost presented by the borrower is as follows:

| S.N. | Particulars | Amount,000 | % |
| --- | --- | --- | --- |
| 1 | Pre- Operating Expenses | 1,747,200 | 2.94% |
| 2 | Civil Works | 30,195,269 | 50.83% |
| 3 | Hydromechanical Works | 3,651,269 | 6.15% |
| 4 | Electro mechanical Works | 8,514,151 | 14.33% |
| 5 | Transmission Line and Switchyard | 1,061,665 | 1.79% |
| 6 | Construction Power | 421,926 | 0.71% |
| 7 | Land Purchased and Development | 153,718 | 0.26% |
| 8 | Office Building/ Camp facilities | 182,645 | 0.31% |
| 9 | Office Equipment Cost | 113,000 | 0.19% |
| 10 | Vehicle Cost | 282,500 | 0.48% |
| 11 | Infrastructure Development Cost | 341,260 | 0.57% |
| 12 | Environment/ Social Mitigation Cost | 422,181 | 0.71% |
| 13 | Project Supervision/ Management & Engineering | 1,191,796 | 2.01% |
| 14 | Physical/ Price Contingency | 3,679,512 | 6.19% |
| 15 | Insurance | 226,000 | 0.38% |
| 16 | Interest During Construction | 7,215,909 | 12.15% |
|  | Total Cost | 59,400,000 | 100% |

Note:

The aforementioned cost has been estimated considering the current market price of the materials and current global scenario.

The Shah Consult International (P) Ltd. has been appointed to carry out due diligence study of the project. The project cost may vary (5%-10%) after finalization of due diligence study of the project. We shall finance maximum up to 75% of total cost as estimated in due diligence study of the project.

However, if the cost presented in the Detailed Project Report (DPR) is lower than the cost estimated in due diligence study and the client decides to proceed with the cost based on DPR with commitment to inject equity in case of cost overrun, this approach could be permitted.

Note: Generation license has clearly mentioned that the project component including civil structures & electromechanical equipment must be prepared for 440 MW capacity. Hence the cost of the same also has been computed.

| S.N. | Particulars | Amount '000 | % |
| --- | --- | --- | --- |
| 1 | Pre- Operating expenses | 1,797,200 | 2.64% |
| 2 | Civil Works | 32,005,802 | 47.07% |
| 3 | Hydromechanical Works | 3,953,419 | 5.81% |
| 4 | Electromechanical Works | 12,539,670 | 18.44% |
| 5 | Transmission Line and Switchyard | 1,246,729 | 1.83% |
| 6 | Construction Power | 421,926 | 0.62% |
| 7 | Land Purchased and Development | 153,718 | 0.23% |
| 8 | Office Building/ Camp facilities | 182,645 | 0.27% |
| 9 | Office Equipment Cost | 113,000 | 0.17% |
| 10 | Vehicle Cost | 282,500 | 0.42% |
| 11 | Infrastructure Development Cost | 510,760 | 0.75% |
| 12 | Environment/ Social Mitigation Cost | 492,181 | 0.72% |
| 13 | Project Supervision/ Management & Engineering | 1,373,052 | 2.02% |
| 14 | Physical/ Price Contingency | 4,257,895 | 6.26% |
| 15 | Insurance | 314,350 | 0.46% |
| 16 | Interest During Construction | 8,355,154 | 12.29% |
|  | Total Cost | 68,000,000 | 100% |

Since the PPA is executed only for a capacity of 298.75 MW, the developer has informed that all project components, except for the electromechanical equipment, will be constructed for 440 MW, as the cost for slight variations is already incorporated in the 298.75 MW capacity. The total cost for 440 MW will be considered only if the PPA is executed for the remaining capacity of 141.25 MW. In the meantime, the Consortium Banks/Financial Institutions will proceed with the total project cost of NPR 59,400 million for financial closure.

Consortium Loan Exposure

In the presence of technical and financial consultants, the developer presented details encompassing financial, technical, and management aspects of the project. The tentative loan exposure of our bank, under the Consortium arrangement, is outlined as follows:

NPR ‘000’

| Bank Name | TL | % | Bridge Gap | Cash Credit | BG | LC | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NMB Bank | 10,000,000 | 22.45% | (5,000,000) | 600,000 | (500,000) | (3,143,000) | 10,600,000 |
| Other Banks | 34,550,000 | 77.55% | - | - | - | (10,857,000) | 34,550,000 |
| Total | 44,550,000 | 100% | (5,000,000) | 600,000 | (500,000) | (14,000,000) | 45,150,000 |

Note:

The BG limit of NPR 50 million has been approved by Prime Commercial Bank Ltd for signing PPA with NEA. However, this limit might be converted into inner limit within Term Loan Limit after the formation of Consortium.

The outstanding during the construction period will be more than the approved limit because we have to take the liability of other Participating Banks and Financial Institution too as Bridge Gap loans and Letters of Credit on risk sharing basis, contingent upon NMB Bank being the Lead or Co-Lead Bank only. This will continue until the COD/moratorium period/final settlement of LC and Bridge Gap Loan.

As a Lead Bank, we have to issue letters of credit (LC) to import electromechanical, switchyard, explosives, hydro-mechanical equipment, materials and equipment related to transmission line. Since the LC cannot be segregated, the issuing bank needs to issue and book a contingent liability for the full value of the LC. However, the risks as well as the liabilities arising for the LC issuing bank shall be shared in the proportion of the Term Loan commitments of each member bank and financial institution. The developer may open usance/sight LC for the import of EM equipment and other equipment for the development of the project. We shall issue usance LC with a maximum usance period of 36 months. In such case, we shall request the developer for doing a forward contract in case of foreign currency other than INR.

Cash Credit shall be advised after COD of the project for management of NEA receivables and other project operation cost.

NAME OF SHAREHOLDERS AND SHAREHOLDING STRUCTURE

The shareholding structure (promoters) dated 2083/2/13 B.S. is as under:

| S.N. | Shareholders Name | Share amount | % holding |
| --- | --- | --- | --- |
| 1 | Aashma Shah | 101,250,000 | 29.35% |
| 2 | Anish Bikram Shah | 30,000,000 | 8.70% |
| 3 | Lok Bahadur Pun | 33,750,000 | 9.78% |
| 4 | Hem Raj Bhatta | 33,750,000 | 9.78% |
| 5 | Mallika Shah | 15,000,000 | 4.35% |
| 6 | Anjay Bahadur Shah | 45,000,000 | 13.04% |
| 7 | Money Plant Investment Pvt. Ltd. | 86,250,000 | 25.00% |
|  | Total | 345,000,000 | 100.00% |

LIST OF PROPOSED DIRECTORS

The present board of directors of the company is as follows:

| S.N. | Board Members | Current BOD | Proposed | Experiences |
| --- | --- | --- | --- | --- |
| 1 | Susan Karmacharya |  | Chairman | - Chairman at Kailash Energy Pvt. Ltd. - 203 MW (Mathillo Budigandaki) - Director at Annapurna Bidyut Bikas Company Pvt. Ltd.- 86.59 MW (Landruk Modi HEP) - Managing Director at Ruby Valley Hydropower Ltd. - 8.47 MW (Menchet Khola HPP) - Managing Director at White Gold Multi Energy Ltd.- 4 MW (Daram Khola HPP) - Executive Chairperson at Madame Khola Hydropower Ltd. (Madame Khola HPP-24 MW) - Former Director at Yambaling Hydropower Ltd. (Yambaling Khola HPP-7.27 MW) - Former Chairman at Eastern Hydropower Ltd. (Pikhuwa Khola Small HPP-5 MW) - Founder Chairman at Money Plant Investment Pvt. Ltd. - Founder at Ojashwi Construction Pvt. Ltd. - Vice President at Independent Power Producers’ Association, Nepal (IPPAN). |
| 2 | Shankar Das Bairagi |  | Director | - Former Chief Secretary for Government of Nepal - Seasoned diplomat who served as the Foreign Secretary of Nepal from October 2015 to October 2020. - Former National Security Advisor |
| 3 | Narendra Ballav Pant |  | Director | - Executive Chairman at Thulo Khola Hydropower Ltd.-22.5 MW - Former Executive Chairman at United Modi Hydropower Ltd. - 10 MW - Former Director at Singati Hydropower Co. Ltd. - 25 MW - Former Managing Director at Taksar Pikhuwa Khola Hydropower Ltd. - 8 MW - Chairman at Pelma Khola Hydropower Pvt. Ltd. - Vice President at IPPAN - Chairman at DEV Group |
| 4 | Iswari Bahadur Adhikari |  | Director | - Founder/CEO at Pathshala Nepal Foundation, Nepal - Chairman at Ruby Valley Hydropower Ltd. - Director at Spark Hydroelectric Co. Ltd. -145 MW - Director at Ganesh Himal Hydropower Co. Ltd. – 22 MW - Managing Director at Pai Investment Co. Ltd. |
| 5 | Lok Bahadur Pun | Chairman | Director | - Director at S.C. Power Co. Pvt. Ltd. since 2007 - Former employee of Department of Electricity Department (DoED) - Holds M. SC. In civil engineering from University of Arizona (1984) |
| 6 | Bhesh Raj Gautam |  | Director | - Extensive knowledge on Banking & Infrastructure financing - MBA degree holder |
| 7 | Dr. Iman Singh Gurung | Director | Director | - Seasoned hydropower Strategist & Investor - PHD from University of Cambridge |
| 8 | Ram Prasad Khanal |  | Director | - Legal Consultant/Corporate Lawyer |
| 9 | Subodh Gautam |  | Director | - Former Banker with experience of over 25 years - Promoter of Doodhpokhari Chepe Hydropower Ltd. - 11 MW |
| 10 | Govinda Dahal |  | Director | - Managing Director at Trishakti Securities Ltd. - Director at Trishakti Equity Fund - Director at Snowfall Hydropower Ltd. - Former Banker |
| 11 | Roshan Shah |  | Project Director | - Project Manager of Madame Khola Hydropower project. - Completed Bachelor of Engineering (BE) from Pokhara University - Completed Advance Course in Steel Structure Engineering from University of Cambridge, London - Worked as Civil Engineer in Mitsubishi Corporation for Construction of Japan/Turkey Underground Metro Project - Worked as Tunnel Engineer for the construction of Dubai Metro Project. - Project Manager in Pikhuwa Khola Small Hydropower Project (5 MW) - Project Manager of Money Plant Namuna Basti |

MAJOR FINANCIAL HIGHLIGHTS (PPA Capacity for 298.75 MW)

NPR 000

|  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- |
| TURNOVER | - | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 |
| TOTAL ASSETS | 59,400,000 | 59,698,999 | 57,878,738 | 56,167,240 | 54,549,013 | 53,021,979 |
| TANGIBLE NET WORTH | 14,850,000 | 16,485,499 | 16,335,863 | 16,673,665 | 17,550,238 | 19,008,054 |
| WORKING CAPITAL | - | 1,328,374 | 1,829,438 | 2,372,440 | 2,964,163 | 3,736,179 |
| GROSS PROFIT | - | 10,419,895 | 10,729,606 | 11,047,359 | 11,358,674 | 11,678,053 |
| NET PROFIT | - | 1,635,499 | 2,077,864 | 2,565,302 | 3,104,073 | 3,685,316 |
| NET PROFIT MARGIN | - | 14.34% | 17.69% | 21.21% | 24.96% | 28.83% |
| GROSS CASH FLOW | - | 6,916,144 | 9,464,998 | 9,760,900 | 10,049,707 | 10,345,948 |
| NET CASH FLOW | - | 6,882,766 | 9,422,593 | 9,708,547 | 9,986,359 | 10,270,737 |
| CURRENT RATIO | - | 1.80 | 1.89 | 1.95 | 1.99 | 2.10 |
| GEARING RATIO | 3.00 | 2.62 | 2.54 | 2.37 | 2.11 | 1.79 |
| INTEREST COVER | - | 1.34 | 1.45 | 1.58 | 1.74 | 1.95 |
| DSCR | - | 1.11 | 1.48 | 1.48 | 1.48 | 1.48 |

MAJOR FINANCIAL HIGHLIGHTS (PPA Capacity for 440 MW)

NPR 000

|  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- | --- |
| TURNOVER | - | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 |
| TOTAL ASSETS | 68,000,000 | 67,597,605 | 64,354,619 | 61,797,833 | 58,433,973 | 55,187,877 |
| TANGIBLE NET WORTH | 17,000,000 | 17,527,605 | 16,822,619 | 16,637,333 | 16,180,474 | 16,351,377 |
| WORKING CAPITAL | - | 150,514 | 164,937 | 163,560 | (619,390) | (1,284,578) |
| GROSS PROFIT | - | 10,419,895 | 10,729,606 | 11,047,359 | 11,358,674 | 11,678,053 |
| NET PROFIT | - | 527,605 | 995,014 | 1,514,714 | 2,093,140 | 2,720,903 |
| NET PROFIT MARGIN | - | 4.62% | 8.47% | 12.53% | 16.83% | 21.28% |
| GROSS CASH FLOW | - | 6,878,067 | 9,428,144 | 9,725,293 | 10,015,411 | 10,312,955 |
| NET CASH FLOW | - | 7,267,300 | 9,007,837 | 9,694,381 | 9,972,694 | 10,257,427 |
| CURRENT RATIO | - | 1.06 | 1.07 | 1.06 | 0.82 | 0.67 |
| GEARING RATIO | 3.00 | 2.86 | 2.83 | 2.71 | 2.61 | 2.38 |
| INTEREST COVER | - | 1.10 | 1.19 | 1.30 | 1.44 | 1.61 |
| DSCR | - | 1.02 | 1.23 | 1.29 | 1.28 | 1.29 |

SUMMARIZED SECURITY (Proposed):							     NPR 000

| PARTICULARS | Amount |
| --- | --- |
| Registered mortgage/Lease charge over project assets and first charge over entire fixed and current assets of the project | 13,333,333 |
| Lien/Assignment of receivable (PPA) from NEA | 2,543,543 |
| Unconditional and Irrevocable Charge on the Power Purchase Agreement (PPA) and Generation License | 45,150,000 |
| Joint & Several Personal Guarantees of Mrs. Susan Karmacharya, Mr. Shankar Das Bairagi, Mr. Narendra Ballav Pant, Mr. Iswari Bahadur Adhikari, Mr. Lok Bahadur Pun, Mr. Bhesh Raj Gautam, Dr. Iman Singh Gurung, Mr. Ram Prasad Khanal, Mr. Roshan Shah, Mr. Subodh Prasad Gautam and the promoters holding 5% or above covering entire credit facilities | 45,150,000 |
| Corporate Guarantee of M/s Madame Khola Hydropower Ltd, M/s Yambaling Hydropower Ltd., M/s Eastern Hydropower Ltd., & M/s Money Plant Investment Pvt. Ltd. covering entire credit facilities | 45,150,000 |
| Internal loan deed/Promissory note to be signed by the borrower | 45,150,000 |
| Pledge over share of Mrs Susan Karmacharya, Mr.Roshan Shah, Mr. Shankar Das Bairagi, Mr. Bhesh Raj Gautam, Mr. Narendra Ballax Pant, Mr.Lok Bahadur Pun, Dr. Iman Singh Gurung, Mr. Iswari Bahadur Adhikari, Mr. Subodh Prasad Gautam, & Mr. Ram Prasad Khanal |  |
| Pledge over shares of M/s Madame Khola Hydropower Ltd, M/s Yambaling Hydropower Ltd, M/s Eastern Hydropower Ltd & Money Plant Investment Pvt. Ltd. |  |
| 2% cash margin for issuance of Letter of Credit & Bank Guarantee | 290,000 |

* The amount is subjected to change after the finalization of consortium. However, the security documents shall be executed covering the entire consortium loan exposure

We propose for not to execute the corporate guarantee & share pledge deeds of Private Equity & Venture Capital (PEVC)s, financial institutions, insurance companies and personal guarantee of director or representative of investor nominated from PEVCs, financial institutions, and insurance companies. Mr. Govinda Dahal is serving as a Director representing Trishakti Equity Fund. So, we propose not to obtain corporate guarantee/share pledge deed of Trishakti Equity Fund and personal guarantee of Mr. Govinda Dahal.

REPAYMENT CAPACITY

We propose to capitalize interest on the Term Loan during construction of the project.  The loan shall be repaid in 12 years after completion of the project/moratorium period, whichever is earlier. The first installment shall be due on subsequent quarter from the date of Commercial Operation of the project or upon completion of the construction moratorium period, whichever is earlier as per the annexed annual repayment schedule (tentative). Adequate cash cushions are expected on Interest Coverage Ratio and Debt Service Coverage Ratio as the cash from the operations are above unity in the projected years thus, indicating a favorable financial position to repay the loans

DETAILS OF PROPRIETOR/ PROMOTER/ PARTNER/ GUARANTOR

The company has been managed by a group of nominated directors from shareholders. Mr. Susan Karmacharya is serving in the capacity of Chairman.

The company hires key staffs for their other management functions.

Capital structure and equity plan

The capital structure of the project is as under:

| Structure | % | Amount (in NPR Mio) |
| --- | --- | --- |
| Equity | 25% | 14,850 |
| Debt | 75% | 44,550 |
| Total | 100% | 59,400 |

Tentative Equity Plan

A. Committed shareholding structure from the Board team member:

| S.N. | Board Members | Committed equity (in NPR Mio) | Net Worth (in NPR Mio) | % of the total equity |
| --- | --- | --- | --- | --- |
| 1 | Susan Karmacharya and Group | 350 | 793 | 2.36% |
| 2 | Shankar Das Bairagi | 20 |  | 0.13% |
| 3 | Narendra Ballav Pant and Group | 100 | 123 | 0.67% |
| 4 | Ishwori Bahadur Adhikari and Group | 100 | 109 | 0.67% |
| 5 | Lok Bahadur Pun and Group | 50 | 89 | 0.34% |
| 6 | Bhesh Raj Gautam and Group | 100 | 295 | 0.67% |
| 7 | Iman Singh Gurung and Group | 300 | 579 | 2.02% |
| 8 | Ram Prasad Khanal and Group | 50 | 93 | 0.34% |
| 10 | Subodh Gautam and Group | 50 | 173 | 0.34% |
| 12 | Govinda Dahal and Group | Representative from Trishakti Equity Ltd. |  |  |
| 13 | Roshan Shah and Group | 100 | 576 | 0.67% |
|  | Total | 1,220 | 2,830 | 8.22% |

B. Committed equity from hydropower companies: in NPR Mio

| S.N. | Name of the company | Project Status | Committed equity | Source | Tentative % of Total Equity |
| --- | --- | --- | --- | --- | --- |
| 1 | Madame Khola Hydropower Ltd. - 24 MW | Operation | 1,320 | Right shares | 8.89% |
| 2 | Yambaling Hydropower Ltd. - 7.27 MW | Operation | 720 | Right shares | 4.85% |
| 3 | Eastern Hydropower Ltd. - 5 MW | Operation | 650 | Right shares | 4.38% |
| 4 | White Gold Multi Energy Ltd. - 4 MW | Under Construction - 70% | 240 | IPO | 1.62% |
| 5 | Thulo Khola Hydropower Ltd. - 22.5 MW | Operation | 1,000 | IPO/Right shares | 6.73% |
| 6 | Taksar Pikhuwa Khola Hydropower Ltd - 8 MW - 8 MW | Operation | 1,000 | Right shares | 6.73% |
| 7 | Ridgeline energy Super Chepe HPP - 9.05 MW | Operation | 200 | Right shares | 1.35% |
|  | Total |  | 5,130 |  | 19.73% |

Profile of M/s Madame Khola Hydropower Ltd.

Madame Khola Hydropower Ltd. (Registered No: 293701/78/079, PAN: 603519507) has developed and been operating Madame Khola Hydropower Project (24 MW) located at Madi Rural Municipality, Kaski. The project achieved commercial operation on 27th December 2025.

The brief financial summary of the Money Plant Investment Pvt. Ltd. is as under:

| Particulars | FY 2081/82 (NPR ‘000) | FY 2080/81 (NPR. ‘000) |
| --- | --- | --- |
| Total Assets | 4,595,818 | 3,143,570 |
| Paid-up Capital | 1,040,000 | 917,068 |
| Sales | - | - |
| Net Profit/Loss | (3,312) | (713) |

Profile of M/s Yambaling Hydropower Ltd.

Yambaling Hydropower Ltd. (Registered No: 269881/078/079, PAN: 302836376) has developed Yambaling Khola Hydropower Project (7.27 MW) located at Sindhupalchowk District. The operation of the project began on 20th February 2024 (2080/11/08) B.S.

The brief financial summary of the Money Plant Investment Pvt. Ltd. is as under:

| Particulars | FY 2081/82 (NPR ‘000) | FY 2080/81 (NPR. ‘000) |
| --- | --- | --- |
| Total Assets | 1,943,304 | 1,905,693 |
| Paid-up Capital | 420,000 | 420,000 |
| Sales | 156,334 | 31,992 |
| Net Profit/Loss | (57,894) | (74,077) |

Profile of M/s Eastern Hydropower Ltd.

Money Plant Investment Pvt. Ltd. (Registered No: 172459/074/075, PAN: 302100400) Eastern Hydropower Ltd. has developed Pikhuwa Khola Hydropower Project (5 MW) located at Bhojpur District. The commercial operation date of the project was 10th June 2019.

The brief financial summary of the Money Plant Investment Pvt. Ltd. is as under:

| Particulars | FY 2081/82 (NPR ‘000) | FY 2080/81 (NPR. ‘000) |
| --- | --- | --- |
| Total Assets | 1,097,324 | 1,127,592 |
| Paid-up Capital | 620,000 | 620,000 |
| Sales | 129,393 | 112,011 |
| Net Profit/Loss | 8,616 | (13,720) |

IPO/Right Shares issuance status of the above hydropower companies

| S.N. | Name of the company | Status |
| --- | --- | --- |
| 1 | Madame Khola Hydropower Ltd. - 24 MW | 10th rank in IPO application list of SEBON (expected to complete right share issuance within 3 years) |
| 2 | Yambaling Hydropower Ltd. - 7.27 MW | IPO approved on 17/11/2082 B.S. (anticipated completion of the right share issuance within 2.5 years) |
| 3 | Eastern Hydropower Ltd. - 5 MW | Right Shares: - 1:1 proposed, currently in Electricity Regulatory Commission (ERC) que. Expected to be completed within FY 2083/84. |
| 4 | White Gold Multi Energy Ltd. - 4 MW | The project has achieved approximately 70% progress and is expected to complete the IPO issuance within 1.5 years. |
| 5 | Thulo Khola Hydropower Ltd. - 22.5 MW | AGM has already approved for IPO issuance. (anticipated completion within a year) |
| 6 | Taksar Pikhuwa Khola Hydropower Ltd - 8 MW | IPO approved on 1/11/2082 B.S. (anticipated completion of the right share issuance within 2.5 years) |
| 7 | Ridgeline Energy Ltd. - 9.05 MW | IPO approved on 22/8/2082 B.S. (anticipated completion of the right share issuance within 2.5 years) |

C. Equity commitment from PEVC and Investment Companies (in NPR Mio)

| S.N. | Name of PEVC | LOI status | Representative | Committed Equity | % of total Equity |
| --- | --- | --- | --- | --- | --- |
| 1 | Nepal Opportunity Fund (NOF -1) | Obtained | Adhyanta Fund Management Ltd. | 150 | 1.0% |
| 2 | Trishakti Equity Fund | Obtained | Trishakti Securities | 1,000 | 6.7% |
|  | i. Total |  |  | 1,150 | 7.7% |
|  | Investment companies |  |  |  |  |
| 1 | Money Plant Investment Pvt. Ltd. | Obtained | Susan Karmacharya | 500 | 3.4% |
| 2 | Smart Investment Ltd. | Obtained | Susan Karmacharya | 120 | 0.8% |
| 3 | Chirau Holding & Investment Pvt. Ltd. | Obtained | Chandra Datta Poudel | 400 | 2.7% |
| 4 | Vision Nepal Ltd. | Obtained | Ram Parsad Khanal | 200 | 1.3% |
| 5 | Vision Investment Company Ltd. | Obtained | Ram Parsad Khanal | 150 | 1.0% |
| 6 | Innovate Investment Company Pvt. Ltd | Obtained | Narendra Ballav Pant | 500 | 3.4% |
| 7 | White Lotus Management Pvt. Ltd | Obtained | Suman Joshi | 200 | 1.3% |
| 8 | Gaumata Investment Company Ltd. | Obtained | Shree Krishna Regmi | 100 | 0.7% |
| 9 | Global Hub Ltd. | Obtained | Bhesh Raj Gautam | 100 | 0.7% |
| 10 | Sumi Investment Company Pvt. Ltd. | Obtained | Min Raj Khadka | 50 | 0.0% |
| 11 | Others (Insurance companies) |  |  | 1,000 | 0.3% |
|  | ii. Total |  |  | 3,320 | 22.40% |

Profile of M/s Money Plan Investment Pvt. Ltd.

Money Plant Investment Pvt. Ltd. (Registered No: 70630/066/67, PAN: 600434641) is an Investment company established with aim to invest in initiatives that contribute to the economic prosperity of the Nepal. The company is committed to invest in the projects and ventures related to Industry, Tourism, Finance, Hydropower, and Financial sector which are vital for thriving economy.

The brief financial summary of the Money Plant Investment Pvt. Ltd. is as under:

| Particulars | FY 2080/81 (NPR ‘000) | FY 2081/82 (NPR. ‘000) |
| --- | --- | --- |
| Total Assets | 336,509 | 450,161 |
| Paid-up Capital | 175,000 | 175,000 |
| Sales |  | 11,172 |
| Net Profit/Loss | (14,56) | 6,627 |

Equity Investment:

| Company Name | Amount |
| --- | --- |
| Ganga Energy Pvt. Ltd. | 12,600,000 |
| Nabil Developers Pvt. Ltd. | 140,000,000 |
| Eastern Hydropower Ltd. | 19,589,300 |
| Yambaling Hydropower Ltd. | 8,150,000 |
| Madame Khola Hydropower Ltd. | 48,089,500 |
| Total | 228,428,800 |

D. Corporate Investor

| S.N. | Foreign Direct Investment | LOI status | Representative | Committed Equity (in NPR Mio) | % of equity |
| --- | --- | --- | --- | --- | --- |
| 1 | THINKK BEETA GROUP LTD. | Obtained | Roshan Shah | 1,400 | 9.4% |

THINKK BEETA GROUP LIMITED was incorporated on 13 Jan-2022 as a private company by shares registered in Hong Kong with registration number: 73724590. The company primarily operates in Import & Export business with partial focus on general trading. The company will inject equity into S.C. Power Co. Pvt. Ltd. as part of its Foreign Direct Investment (FDI).

E. Other Promoters (in NPR Mio)

| S.N. | Partners Name | Committed equity | % | Related Group |
| --- | --- | --- | --- | --- |
| 1 | Suraj Tuladhar & Group | 400.00 | 2.69% | Goodwill Finance |
| 2 | Dhan Bahadur Shrestha | 100.00 | 0.67% | Eastern HPP |
| 3 | Chandra Datta Poudel/ Group | 400.00 | 2.69% | Chirau Group |
| 4 | United Group | 100.00 | 0.67% | United School |
| 5 | Bishnu Ojha & Group | 100.00 | 0.67% | Broker No -38 (Dipshika) |
| 6 | Raj Kumar Timilsina & Group | 100.00 | 0.67% | Broker No -30 (Vision Securities) |
| 7 | Shankar Basyal & Group | 50.00 | 0.34% | Environmentalist |
| 8 | Er. Rewant Kumar Rawat | 50.00 | 0.34% |  |
| 9 | Ramesh Pandey & Group | 100.00 | 0.67% | Hardik Hotel |
| 10 | Om Basnet & Group | 100.00 | 0.67% |  |
| 11 | Milan Khatiwada & Group | 100.00 | 0.67% |  |
| 12 | Ashma Shah | 150.00 | 1.01% |  |
| 13 | Anish Bikram Shah | 60.00 | 0.40% |  |
| 14 | Ajay Bahadur Shah | 80.00 | 0.54% |  |
| 15 | Mallika Shah | 50.00 | 0.34% |  |
| 16 | Hem Raj Bhatta | 50.00 | 0.34% |  |
| 17 | Dr. Basant Giri | 50.00 | 0.34% |  |
| 18 | Pradip Giri & Group | 100.00 | 0.67% |  |
|  | Total | 2,140.00 | 14.41% |  |

F. Other Promoters (in NPR Mio)

| S.N. | Others | Proposed Equity | % of the total equity |
| --- | --- | --- | --- |
| 1 | Local | 140.00 | 0.94% |
| 2 | Others | 350.00 | 2.36% |
|  | Total | 490.00 | 3.30% |

Risk- Project Management

Being a highly capital-intensive project having long gestation period, project completion risk is relatively high.

Mitigation:

- The promoter has committed to inject 30% of the upfront equity before the first drawdown of the Term Loan. As per the tentative equity injection plan provided by the client, the collection of equity from major companies is anticipated as below:

| S.N. | Companies/Investor/Equity partners | Proposed Equity (NPR Mio) |
| --- | --- | --- |
| 1 | Equity from the Board Team member | 1,320 |
| 2 | Committed equity from hydropower companies | 5,130 |
| 3 | Equity commitment from PEVC | 1,150 |
| 4 | Investment companies | 3,320 |
| 5 | Corporate Investor | 1,400 |
| 6 | Strategic Partners | 2,040 |
| 7 | Other promoters | 490 |
|  | Total | 14,850 |

*Details mentioned in the equity plan section.

Considering the strong network and track record of this group, it is reasonable to anticipate that the developer will inject equity punctually, ensuring the timely completion of the project.

Risk- Hydrological

Similar to many other projects in the country, the project may face challenges in supplying sufficient power to Nepal Electricity Authority (NEA) during the dry season

Mitigation:

- The Tila River is perennial, with about 7% of the catchment area above 5000 masl, contributing permanent snowmelt; the rest is mostly barren land and forest with minimal settlements, ensuring consistent flow. Besides, availability of long-term hydrological data from Department of Hydrology and Meteorology (DHM) gauging stations upstream and downstream, in the source river, increases confidence in the hydrological estimates.

Risk- Promoters Conflict

There are many promoters in the company. Conflict among promoters may cause delay in commissioning of the project.

Mitigation

- The current directors demonstrate a strong commitment to the timely completion of the project. Additionally, as a group of professional individuals, they recognize the importance of working collaboratively and avoiding conflicts to ensure the success of a project of this magnitude.

Risk - Power Evacuation

As per the Power Purchase Agreement (PPA), the project has been assigned to the NEA's proposed Chhinchu (Sukhet) substation for the power evacuation. With this arrangement, the project is required to construct approximately 80 km of 440 kV D/C transmission line from the project switchyard to the proposed substation.

Mitigation

- Since the construction of Chhinchu (Surkhet) substation is yet to be initiated, the developer has proposed to change the evacuation point to the RPGCL's Phukot 440 kV Substation which is just 6 Km from the switchyard of the project.

RPGCL is constructing Transmission Line (TL) from Phukot (Kalikot) - Betan (Surkhet) - Dodhara (Kailali) 400 kV D/C line and the associated 3 substations. RPGCL anticipates completing the project (TL) by FY 2088/99 B.S. In the rare event that RPGCL is unable to raise the required equity on its own, Independent Power Producers (IPPs) of nearby projects could step in and help complete the Phukot - Betan - Dodhara Transmission Line on time when the projects in the corridor are commissioned. The Phukot-Betan-Doodhara Transmission Line can be developed jointly under an equity participation model with RPGCL, with an estimated cost of NPR 10,000 Mio. Some 4,000 megawatts of electricity generated from Karnali basin, including Phukot-Karnali, Betan-Karnali, Tila I and Tila II hydropower projects will be connected to the national transmission grid through this Tranmission Line. Grid connection MoUs for several hydropower projects, totaling a capacity of more than 1500 MW [Tila – 1 HPP 440 MW, Tila 2 HPP (HPP) 420 MW, Humla Karnali 1 HPP - 235 MW, Humla Karnali 2 HPP- 335 MW, etc], have been concluded with RPGCL to evacuate energy from the Karnali Corridor Transmission Line.

The details of cost & proposed equity participation model for the transmission line, if RPGCL is unable to raise the equity on its own, is as under:

| S.N. | Particulars | Amount (in NPR Mio) | Remarks |
| --- | --- | --- | --- |
|  | Total Length from Phukot Substation to Kamdev Dhodhara |  | 121 - 125 Km |
|  | Tentative Cost Per KM Including ROW |  | NPR 70-80 Mio |
|  | Total Transmission Line Cost | 10,000 |  |
|  | Loan (70%) | 7,000 |  |
|  | Debt (30%) | 3,000 |  |
|  | Equity Participation |  |  |
|  | RPGCL | 780 | 51% as per plan |
|  | Independent Power Producers (IPPs) | 2,220 | Equity participation from IPPs |
|  | Tila 1 HPP [440 MW] - NPR 390.7 Mio |  |  |
|  | Tila 2 HPP [420 MW] - NPR 373 Mio |  |  |
|  | Phukot Karnali HPP [480 MW]- NPR 426.2 Mio |  |  |
|  | Betan Karnali HPP [439 MW] - NPR 610.9 Mio |  |  |
|  | Others [472 MW] - NPR 419.1 Mio |  |  |

The wheeling charge will be finalized through mutual agreement in due course. This also serves as a source of income for the equity partners, as they can charge the wheeling fee for the project using this transmission line (TL).

Risk - Social Risk

Various social factors are to be considered while developing the hydropower project. In recent years, tendencies of cashing opportunities for vested interests in the name of social interests are growing.

Mitigation

- The Board of Directors includes an experienced promoter who has experience of establishing positive relationships with the people in the project's affected area. This demonstrates their ability to effectively handle challenges. As a result, the risk of project disruption due to social issues is low. Furthermore, a project of this size (440 MW) brings economic prosperity to the region, which also reduces the likelihood of local disruption.

Risk- Construction

The developers are new to the development of the Peaking Run-of-River (PROR) project with Tunnel, and as a result, they may encounter challenges in addressing design-related issues and performance optimization. This knowledge gap could potentially lead to delays in project commissioning or even changes in management.

Mitigation

- The water handing system and civil components are comparatively smaller considering the project size, with the detailed design planned to be executed by Shah Consultant International Pvt Ltd. to leverage their extensive expertise. Furthermore, the probable civil contractor’s prior experience in constructing underground components in challenging terrain further enhances the project’s potential successful execution.

Risk – Operation Modality

As a PROR project of 420 MW is also under development just upstream of this project, there could arise risk of the plant’s operation, especially during peak times.

Mitigation:

Having PROR projects either upstream or downstream in the same source river is getting more and more common as many projects are being developed. Any minor uncertainty regarding smooth plant operation for this project is not a “stand-alone” case. There is no specific modus operandi planned by either DoED or NEA as of late. All of the PPAs that have been done up to now is by considering the projects as standalone entities. Based on numerous discussions with NEA regarding this, finalization of “operation modality” of power plants will be done during the time of the projects’ commissioning and testings. It could be expected that feasible, doable and justifiable operation modalities will be in place by NEA for all those projects whose flow availability could get impacted due to them being downstream from a PROR project.

Risk – Financial

The financial assessment has been conducted based on the financial statements and contract energy table of PPA, along with the Detail Project Report (DPR). Major assumptions of financial projection are as under:

- Revenue of the project comes from sale of electricity to NEA. As per the PPA, the company will submit the bill to NEA in every month after reading the sold energy by the personnel of NEA. NEA will pay the bill within maximum period of 45 days of the submission.

- Energy Purchasing Rates by NEA as per PPA is as under:

Dry Peak- NPR 10.55; Dry Off Peak- NPR 8.40; Wet - NPR 4.80 per unit during 1st year (6 months dry and 6 months wet season)

- Wheeling charge of 0.4 paisa per unit(kWh) is considered every year

- The loan tenure has been considered for 12 years including 5 years of moratorium period.

- Interest rate at 11% p.a. is applied for financial assessment.

- For PROR hydropower projects having capacity over 40 MW, the projects don’t need to pay income tax for 15 years if financial closure is concluded within Chaitra 2085.

Profitability

The operating & administrative costs are relatively low for hydro projects. As an accepted 	principle, there is provision of royalty at NPR 100 per kW + 2% of annual revenue for more than 	1 MW project up to 15 years from COD and other operating costs have been assumed for 10.3% 	of sales revenue.

The component of interest and depreciation is relatively higher for long term projects. The 	depreciation is calculated at straight line basis. The interest component of the loan is around 	42.7% of the total revenue in the first year which shall gradually decrease on repayment of loans.

The project is expected to generate total revenue of NPR 11,408 Million during first year of commercial operation which shall grow up to NPR 14,144 Million from 9th year onwards.

The net profit margin of the project during 1st year shall be around 14.3%, which will be increased in projected years due to reduction in interest paid and depreciation remaining constant.

Assets & Liability Management

- Hydropower development demands long term investments for Capex needs. Once the project starts its commercial operation, except for some regular maintenance, the incremental investment needs are minimal.

- The total estimated Term Loan financing needs of the project is proposed to NPR 44,550 Million approx. from total project cost of NPR 59,400 million, financed under 75:35 debt equity proportions (with IDC financing)

- The net worth of the company shall gradually improve with repayment of debts from cash flows generated. The net profit margin shall also improve over the years with reduction of interest component of debt.

- There are also small components of short-term assets and liabilities like – receivables from NEA, Cash, and short-term payables.

Cash Flows

The cash flows are positive throughout the project period, cash surplus after CADA. At the projected level of energy generation, the project is expected to generate adequate annual cash surplus to repay all the debt obligations.

Others

- Majority of cash from operation are utilized for repayment of loan and serving of interest. After servicing of debt, there remains surplus cash every year.

- Debt Service Coverage Ratio (DSCR), Current ration & Interest Coverage ratio is estimated to be above unity throughout the projected period.

- The company shall be able to maintain positive cash from 1st year of operation even with sensitization of energy by 26%.

FACILITY STRUCTURE RISK

Term Loan: The Borrower may utilize Term Loan limit of NPR 44,550 Million to finance capital expenditure for construction of Tila-1 Hydropower Project (PRoR). Such capital expenditure may include total project cost as mentioned above including purchase of land, civil construction, purchase of hydro plants, materials, equipment’s, pipes etc.

- All the drawdown shall be made available through the current account of borrower and the disbursements shall be made against the bills/invoices certified by consortium appointed authorized ‘A’ Class auditor/ certified by the Bank appointed valuator/consultant/ documents against Letter of Credit/against VAT Bills. The first drawdown shall be made only after the injection of 30% committed equity portion in the form of cash and/or capital expenditure/preliminary expenses duly certified by a Class “A” Auditor and/or verified against the valuation report valued by an independent valuator/consultant appointed by the Bank.

- Drawdown under term loan shall be allowed up to NPR 44,550 Million or 75% of project cost (with IDC financing) of the due diligence report

- Payment shall be made directly to the suppliers/contractors through Bank as far as practicable.

- Repayment of the Term Loan will be over a period of 17 years including principal and interest moratorium period of 5 years for payment of principal from the date of first disbursement of Term Loan.

- During moratorium period, interest on the Term Loans will be capitalized within the approved budget of IDC. The principal repayment shall be started after subsequent quarter of commercial operation date (COD) of the project or as decided by the Bank. Actual amount of installment will be prepared after completion of moratorium period based or commercial operation of the project.

Letter of Credit (LC)

Letter of Credit facility shall be utilized for the import of Electro Mechanical Equipment, switchyard, explosives, Materials, Metal items and other required items/equipment’s etc. for the proposed project.

The payout under LC shall be managed from disbursement of term loans.

The LC shall have a validity of maximum of 36 months as the electro mechanical components like turbine; generator, etc. are manufactured as per the customized requirements of the applicant. Further, a portion of LC of around 5% of the LC value may remain outstanding as margin for warranty which needs payout after the period of warranty cover. Hence, the equivalent portion of such value may have to be extended for further period after the arrival of goods. In addition, the developer may open usance/sight LC for the import of EM equipment and other equipment for the development of project. We shall issue usance LC with maximum usance period 36 months.

Bridge Gap Loan (BGL)

A revolving facility of NPR 5,000 million within Term Loans shall be made available to the borrower for financing the bills until the consultant appointed by Bank verifies the bills on behalf of Bank. Each bridge gap loan shall be provided for a maximum period of 150 days by when it will be converted into Term Loan after obtaining bills verified by financial consultant.

After accumulation of outstanding loan under this Bridge Gap Loan, drawdown under Term Loan and proceeds from disbursement of Term Loan will be used for repayment of Bridge Gap Loan. The limit will be available for the construction period only.

Bank Guarantee

We propose BG limit within Term loan of NPR 500 Million backed by 2% cash margin to provide performance Bank Guarantee for ensuring the RCOD date as per PPA Clause and to acquire necessary approval for the project development.

Cash Credit Facility

Cash Credit facility of NPR 600 million shall be provided for NEA’s receivables management & other cash management for one year on renewable basis. The facility shall be provided by Bank after commercial operation of the project and the limit will be turnover from the monthly released NEA’ bills. As per PPA, it will take maximum 60 days (i.e. 7-10 days bills preparation and 45-50 days is due date for payment) from the date of billing to release the payment by NEA. Based on the maximum energy generation period and time period for realization of receivables from NEA, we have proposed NPR 600 million as cash credit facility for NEA’s receivables management & other cash management for one year on renewable basis. The fund shall be utilized only to manage the mismatch of receivables & scheduled payment amount and the limit shall be advised to the borrower only after Commercial Operation of the project.

This facility shall be provided for a maximum period of one year on regular basis against bills receivable from NEA and is subject to annual review. However, the facility is to be repayable on demand.

CREDIT GRADE

The external Credit Grading: CARE - NP BB- [indicates a moderate risk of default regarding the timely servicing of financial obligations]

LIST OF WAIVERS

- Proposed moratorium period of 5 years or actual COD (until cash inflows begin from project operations/production) whichever is earlier.

- Total exposure during construction may exceed approved Term Loan limit.

- Facilitate LC opening for blasting materials (explosion).

Justification:

- As per Nepal Rastra Bank directive 02/82 clause no 7, credit facilities having moratorium period of more than one year requires approval from board of directors. Moratorium period of 5 years is recommended on the following grounds:

- We propose to provide moratorium period of 5 years citing various unavoidable circumstances in the project though they have scheduled commissioning of the project earlier.

- Hydropower Project requires long gestation period to come into operation and generate revenue.

- In case, project runs smoothly at projected level before expiry of moratorium period, repayment may be started before completion of 5-year moratorium period.

REASONS FOR RECOMMENDATION

The proposal has been recommended at DE ratio of 75:25 based on the following:

1. Project Specific:

- The project's first-year annual revenue is about 3.82 crore/MW based on the installed capacity of 298.75 MW (excluding reserve margin during 5 wet months), which is favorable even for a 6:6 months PPA type PROR project.

- The project site has easy access via the Karnali Rajmarg National Highway, located about 150 km from Surkhet, with the highway passing close to the powerhouse and headworks.

- Good financial indicators having sufficient cash flow. There is positive cash flow of the project from first year of operation even if the annual energy generation drops down by 26% For PROR project having capacity over 40 MW, the hydropower projects don’t need to pay income tax for 15 years if financial closure is concluded within Chaitra 2085.

- Even considering total cost of 440 MW capacity and revenue of only 298.75 MW, the project is financially viable.

- Due to the high gross head of 503.3 m, civil components are relatively smaller compared to projects of similar size

- The transmission line to NEA’s interconnection point is only about 6.5 km, which is short for a project of this scale and could be constructed jointly with the upstream Tila-II HEP (420 MW).

- Geological and hydrological studies, including sub-surface investigations with test tunnels and sediment measurements, confirm robust conditions at project sites

2. Promoter Specific:

- The group has a good reputation and possesses a good net worth & network to inject equity for the project's development.

- The Board also composes a hydropower experts and technical persons, hence smooth project execution is anticipated.

- The group has appointed a skilled technical team to oversee detailed design and project monitoring. The project director, Er. Roshan Shah, brings extensive experience to the project, further enhancing oversight. His involvement in previous projects (Madame Khola HPP, Yambaling Khola HPP & Pikhuwa Khola HPP ensures effective decision-making and risk mitigation throughout the project lifecycle.

- The group is dedicated to adhering to mitigation measures proposed in the Initial Environmental Examination (IEE) study report, environmental and social (E&S) practices, including occupational health and safety practices (OHS).

SCHEDULE OF LIMITS

| NO | FACILITY | FB/NFB | CURRENT NPR 000 | PROPOSED NPR 000 | O/S NPR 000 | REV. / TERM. | TENURE | PURPOSE/ REPAYMENT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Term Loan (TL) | FB | - | 10,000,000 | - | Term. | 17 years | To incur Capex for the construction and development of the proposed hydropower project. The loan shall be repaid within 17 years from the date of initial disbursement of which the initial 5 years shall be the principal moratorium period. We propose to capitalize interest on term loan during construction of project. However, the developer may repay interest from their own source. The repayment schedule of the loan shall be drawn upon completion of the moratorium period. Financing under the Term Loan shall be restricted to a maximum of 75:25 ratio (with IDC financing) upon presentation of running bills to the bank and duly certified by the auditors. The first term loan drawdown shall be provided upon injection of 30% committed equity certificated by ‘A’ class auditors in form of cash and/or capital expenditure. |
| 2. | Cash Credit | FB | - | 600,000 | - | Rev. | For a maximum period of one year on regular basis. | For NEA’s receivables & cash management |
| 3. | Letters of Credit (LC) (within TL) | NFB | - | 14,000,000 | - | Term. | Within the tenure of Term Loan or as per LC payment Terms. | To import machineries, equipment and others components for developing hydropower project. We shall issue sight LC or usance LC for maximum period of 36 months from the date of issuance. |
| 4. | Bridge Gap Loan (BGL) (within TL) | FB | - | 5,000,000 |  | Rev. | 1 year | To facilitate temporary financing requirements of the project, pending disbursal under approved Term Loan. During Moratorium period or final disbursement of Term Loan which occurs earlier within term loan limit of all banks financing on risk sharing basis. Each bridge gap loan shall be provided for a maximum period of 150 days |
| 5. | Bank Guarantee (BG) (within TL) | NFB | - | 500,000 | - | Rev. | The validity of BG is as per PPA and bank guarantee to obtain necessary approval required for project execution | Providing performance Bank Guarantee for ensuring the RCOD date as per PPA Clause and to acquire necessary approvals for the project development. |
| TOTAL FB |  | - |  | 10,600,000 | - |  |  |  |
| TOTAL NFB |  | - |  | 3,643,000 |  |  |  |  |
| TOTAL |  | - |  | 10,600,000 |  |  |  |  |
| FCDL |  | - | - | 251,440 | - |  |  |  |
| TOTAL GROUP LIMIT |  |  |  |  |  |  |  |  |

Financial Indicator (for 298.75 MW)                                                                                                                                    NPR 000

|  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TURNOVER | - | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 | 13,118,668 | 13,456,623 | 13,806,476 |
| TOTAL ASSETS | 59,400,000 | 59,698,999 | 57,878,738 | 56,167,240 | 54,549,013 | 53,021,979 | 51,708,770 | 49,826,215 | 48,179,717 |
| TANGIBLE NET WORTH | 14,850,000 | 16,485,499 | 16,335,863 | 16,673,665 | 17,550,238 | 19,008,054 | 21,080,645 | 23,073,940 | 25,793,343 |
| WORKING CAPITAL | - | 1,328,374 | 1,829,438 | 2,372,440 | 2,964,163 | 3,736,179 | 4,632,920 | 4,960,315 | 5,479,217 |
| GROSS PROFIT | - | 10,419,895 | 10,729,606 | 11,047,359 | 11,358,674 | 11,678,053 | 11,982,094 | 12,288,384 | 12,605,586 |
| NET PROFIT | - | 1,635,499 | 2,077,864 | 2,565,302 | 3,104,073 | 3,685,316 | 4,300,090 | 4,963,295 | 5,689,403 |
| NET PROFIT MARGIN | - | 14.34% | 17.69% | 21.21% | 24.96% | 28.83% | 32.78% | 36.88% | 41.21% |
| GROSS CASH FLOW | - | 6,916,144 | 9,464,998 | 9,760,900 | 10,049,707 | 10,345,948 | 10,626,106 | 10,907,835 | 11,199,774 |
| NET CASH FLOW | - | 6,882,766 | 9,422,593 | 9,708,547 | 9,986,359 | 10,270,737 | 10,538,349 | 10,806,543 | 11,083,663 |
| CURRENT RATIO | - | 1.80 | 1.89 | 1.95 | 1.99 | 2.10 | 2.20 | 2.14 | 2.12 |
| GEARING RATIO | 3.00 | 2.62 | 2.54 | 2.37 | 2.11 | 1.79 | 1.45 | 1.16 | 0.87 |
| INTEREST COVER | - | 1.34 | 1.45 | 1.58 | 1.74 | 1.95 | 2.21 | 2.57 | 3.09 |
| DSCR | - | 1.11 | 1.48 | 1.48 | 1.48 | 1.48 | 1.50 | 1.52 | 1.55 |

Sensitivity Analysis														NPR 000

|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Actual Revenue | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 | 13,118,668 | 13,456,623 | 13,806,476 | 14,144,367 |
| Revenue @90% | 10,267,378 | 10,571,537 | 10,883,673 | 11,190,506 | 11,505,374 | 11,806,802 | 12,110,961 | 12,425,829 | 12,729,930 |
| Revenue @80% | 9,126,558 | 9,396,922 | 9,674,376 | 9,947,117 | 10,226,999 | 10,494,935 | 10,765,299 | 11,045,181 | 11,315,493 |
| Revenue @74% | 8,442,066 | 8,692,153 | 8,948,798 | 9,201,083 | 9,459,974 | 9,707,815 | 9,957,901 | 10,216,792 | 10,466,831 |
| Operating Expenses | 2,197,330 | 2,253,716 | 2,312,485 | 2,373,440 | 2,436,692 | 2,501,711 | 2,569,113 | 2,639,417 | 2,711,714 |
| Principal | 1,336,500 | 1,670,625 | 2,049,300 | 2,494,800 | 2,984,850 | 3,385,800 | 3,875,850 | 4,365,900 | 4,900,500 |
| Interest | 4,875,369 | 4,714,572 | 4,515,183 | 4,256,383 | 3,961,740 | 3,616,868 | 3,224,215 | 2,777,657 | 2,275,356 |
| Bank Obligation | 6,211,869 | 6,385,197 | 6,564,483 | 6,751,183 | 6,946,590 | 7,002,668 | 7,100,065 | 7,143,557 | 7,175,856 |
| Tax | - | - | - | - | - | - | - | - | - |
| Surplus/ (Deficit) |  |  |  |  |  |  |  |  |  |
| Actual Revenue | 2,998,999 | 3,107,239 | 3,216,002 | 3,309,273 | 3,400,466 | 3,614,290 | 3,787,445 | 4,023,503 | 4,256,797 |
| Revenue @90% | 1,858,179 | 1,932,624 | 2,006,705 | 2,065,883 | 2,122,092 | 2,302,424 | 2,441,783 | 2,642,855 | 2,842,360 |
| Revenue @80% | 717,359 | 758,009 | 797,408 | 822,493 | 843,717 | 990,557 | 1,096,121 | 1,262,207 | 1,427,923 |
| Revenue @74% | 32,867 | 53,240 | 71,830 | 76,460 | 76,692 | 203,437 | 288,723 | 433,819 | 579,261 |

Financial Indicator (for 440 MW)                                                                                                                           NPR 000

|  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TURNOVER | - | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 | 13,118,668 | 13,456,623 | 13,806,476 |
| TOTAL ASSETS | 68,000,000 | 67,597,605 | 64,354,619 | 61,797,833 | 58,433,973 | 55,187,877 | 52,268,906 | 49,344,754 | 46,680,460 |
| TANGIBLE NET WORTH | 17,000,000 | 17,527,605 | 16,822,619 | 16,637,333 | 16,180,474 | 16,351,377 | 17,359,406 | 18,923,254 | 21,282,459 |
| WORKING CAPITAL | - | 150,514 | 164,937 | 163,560 | (619,390) | (1,284,578) | (1,673,639) | (2,042,383) | (2,176,768) |
| GROSS PROFIT | - | 10,419,895 | 10,729,606 | 11,047,359 | 11,358,674 | 11,678,053 | 11,982,094 | 12,288,384 | 12,605,586 |
| NET PROFIT | - | 527,605 | 995,014 | 1,514,714 | 2,093,140 | 2,720,903 | 3,388,030 | 4,113,847 | 4,909,206 |
| NET PROFIT MARGIN | - | 4.62% | 8.47% | 12.53% | 16.83% | 21.28% | 25.83% | 30.57% | 35.56% |
| GROSS CASH FLOW | - | 6,878,067 | 9,428,144 | 9,725,293 | 10,015,411 | 10,312,955 | 10,594,500 | 10,877,660 | 11,171,052 |
| NET CASH FLOW | - | 7,267,300 | 9,007,837 | 9,694,381 | 9,972,694 | 10,257,427 | 10,525,356 | 10,793,704 | 11,070,864 |
| CURRENT RATIO | - | 1.06 | 1.07 | 1.06 | 0.82 | 0.67 | 0.63 | 0.59 | 0.61 |
| GEARING RATIO | 3.00 | 2.86 | 2.83 | 2.71 | 2.61 | 2.38 | 2.01 | 1.61 | 1.19 |
| INTEREST COVER | - | 1.10 | 1.19 | 1.30 | 1.44 | 1.61 | 1.84 | 2.14 | 2.59 |
| DSCR | - | 1.02 | 1.23 | 1.29 | 1.28 | 1.29 | 1.31 | 1.32 | 1.35 |

Sensitivity Analysis														NPR 000

|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Actual Revenue | 11,408,198 | 11,746,153 | 12,092,970 | 12,433,896 | 12,783,749 | 13,118,668 | 13,456,623 | 13,806,476 |
| Revenue @90% | 10,267,378 | 10,571,537 | 10,883,673 | 11,190,506 | 11,505,374 | 11,806,802 | 12,110,961 | 12,425,829 |
| Revenue @82% | 9,354,722 | 9,631,845 | 9,916,236 | 10,195,795 | 10,482,674 | 10,757,308 | 11,034,431 | 11,321,311 |
| Operating Expenses | 2,212,796 | 2,268,472 | 2,326,651 | 2,387,105 | 2,450,003 | 2,514,703 | 2,581,952 | 2,652,216 |
| Principal | 1,530,000 | 1,938,000 | 2,371,500 | 2,907,000 | 3,417,000 | 3,927,000 | 4,488,000 | 5,023,500 |
| Interest | 5,576,888 | 5,391,758 | 5,160,696 | 4,862,741 | 4,521,934 | 4,125,026 | 3,669,915 | 3,154,146 |
| Bank Obligation | 7,106,888 | 7,329,758 | 7,532,196 | 7,769,741 | 7,938,934 | 8,052,026 | 8,157,915 | 8,177,646 |
| Tax | - | - | - | - | - | - | - | - |
| Surplus/ (Deficit) |  |  |  |  |  |  |  |  |
| Actual Revenue | 2,088,514 | 2,147,923 | 2,234,123 | 2,277,049 | 2,394,812 | 2,551,939 | 2,716,757 | 2,976,615 |
| Revenue @90% | 947,694 | 973,308 | 1,024,826 | 1,033,660 | 1,116,437 | 1,240,072 | 1,371,094 | 1,595,967 |
| Revenue @82% | 35,038 | 33,616 | 57,389 | 38,948 | 93,738 | 190,579 | 294,564 | 491,449 |

SCHEDULE OF SPECIFIC COVENANTS/CONTROLS

The covenants and control measures shall be as per the norms set by the consortium and shall be as per follow or as the norm set by the Bank in upcoming Loan Agreement:

- Debt equity ratio shall be maintained at 75:25 (with IDC financing) at all times. Any reduction in the estimated project cost shall attract revision of total credit facility limits as well.

- 30% of total committed equity portion to be injected upfront in form of Cash or Capital Expenditure, which need to be duly verified by the appointed financial/technical consultant by consortium

- A loan arrangement fee of 0.50% of the approved Term Loan shall be levied. The Lead/Co-Lead Banks shall retain half of the fee of the term loan (Lead and Co-Lead Banks shall share fee on proportionate basis based on their loan exposure) and balance half shall be shared amongst the Consortium Banks including the Lead/Co-Lead Banks in proportion to their respective participation in the Term Loan financing. The management fee on term loan shall become due for payment on the date of signing of Loan agreement. The Lead Bank shall charge fee on the Cash Credit facility. The loan arrangement fee is non-refundable even if the loan is not disbursed due to whatsoever reason. Renewal fee on the Cash Credit facility shall be charged as per STC of the Bank at the time of renewal.

- A commitment Fee of 1% p.a. shall be charged if the utilization of loan is less than 60% by the end of drawdown period

- A maintenance reserve account is to be maintained with the bank wherein 2% of the monthly sales is to be deposited every month. The amount shall be used for maintenance of the project and to meet urgent requirements of funds in emergency.

- Cash Margin of 2% of the value of the LCs and Guarantees shall be placed in a non-interest-bearing margin account with the Lead Bank.

- An agency fee at 0.075% on loan outstanding or minimum NPR 4 Mio shall be charged by the Lead Bank

- Commission rate for the opening of Letters of Credit (LC) shall be 0.1% per quarter or minimum NPR 2,500.00 per quarter or part thereof. Commission on issuance of the Bank Guarantee shall be 0.35% per quarter or minimum NPR 2,000.00 per quarter.

The commission on Letter of Credit shall be shared amongst the Consortium Banks/FI in proportion to their respective participation in the Term Loan financing. The LC liability shall also be shared among the Consortium Banks/FI in pro-rata basis, upon the advice of the Lead Bank

- The interest rate on the Term Loan shall be charged on the basis of weighted average base rate of the Consortium Banks plus 1.75% risk premium. However, interest rate shall not be below than base rate plus 0.25% premium of any individual Bank. The applicable interest rates on the Term Loan shall be changed accordingly with the change in rolling average WABR of the Participating Banks every month and shall be effective from the 1st day of Nepali months. The interest shall be payable on a quarterly basis on Ashad, Ashwin, Poush and Chaitra End of Nepali calendar. The interest will be calculated on a daily basis on the outstanding debt balances under the facility and charged to the debit of the Borrower’s account. The interest shall be capitalized to the principal loan till the moratorium period. The interest rate on the Bridge Gap loan and Cash Credit shall be 0.25% higher than that of the Term Loan.

- The consortium reserves the right to review the entire credit facilities and terms on the basis of Technical & Financial Due Diligence Report submitted by consultant appointed by the Lenders

E&S UPDATES

# PROJECT OVERVIEW & BASELINE PARAMETERS

The Tila-1 Hydropower Project (Tila-1HEP) is a 440 MW Peaking Run-of-River (PROR) hydroelectric project located along the Tila River in the Kalikot District, Karnali Province of Western Nepal. The project features an impoundment reach extending 898 meters along the main Tila River and 403 meters along the Ruru River due to 55m dam, 13.7 Km long headrace tunnel and an underground powerhouse.

Key Technical & Physical Baseline

- Hydrology & Geomorphology: The project utilizes a snow-fed river system characterized by high seasonal sediment loads.

- Geological Setting: Located in the Lesser Himalaya (Crystalline to Metasedimentary sequence) with mixed granite at the headworks. Currently, no major or active landslides exist within the immediate project footprint.

- Footprint & Land Tenure: As per EIA, project requires 185.92 ha of land (150.27 ha government, 35.65 ha private belonging to 306 directly affected families). 56.52 ha is for permanent structures and 129.39 ha for temporary facilities. No physical displacement will occur. Overall land acquisition requirements are expected to significantly decrease due to ongoing client optimization and newly built local roads.

- Socio-Demographic Profile: Predominant ethnic groups in the Khadachakra Municipality include Brahmin, Thakuri, and Dalit communities (with high Dalit concentrations in Daha and Manma Village). There are no indigenous peoples living within the direct project footprint.

- Ecosystem Profile: The project site does not fall within any national park or protected conservation area.

# PRELIMINARY ESG RISK RATING MATRIX (HYDROSELECT SCREENING)

Based on the preliminary Hydroselect screening framework developed by Hydropower Sustainability Alliance (HSA), the project demonstrates a manageable E&S risk profile across key performance standards, with specific moderate risks requiring targeted contractual covenants.

| ESG Risk Dimension | Rating | Core Drivers & Key Considerations |
| --- | --- | --- |
| 1. Societal Contribution | Low | Major local infrastructure upgrade, power generation, and community investments. |
| 2. Labour & Working Conditions | Moderate | Workforce peak of ~1,200 workers create labor influx risks requiring camp management. |
| 3. Water Quality, Erosion & Sedimentation | Moderate | High sediment flow, ~719,000 m³ muck management, and BPCP site wastewater handling. |
| 4. Infrastructure & Community Safety | Moderate | Public safety risks from tunnel blasting, heavy traffic, and temple relocation of temple and suspension bridge. |
| 5. Resettlement & Livelihood Impacts | Low | Zero physical displacement observed; land acquisition is localized and manageable. |
| 6. Biodiversity & Habitat Connectivity | Moderate | Potential disruption to migratory fish species and terrestrial wildlife corridors. |
| 7. Indigenous Peoples | Very Low | No indigenous populations reside within the direct project footprint. |
| 8. Critical Cultural Features | Low | Targeted mitigation for 3 cremation sites and 1 temple relocation. |
| 9. Political Risks | Low | Stable project proponent alignment and strong local community willingness (97%). |
| 10. Community Acceptance & License | Low | 97% willingness to cooperate, provided CSR and fair compensation are met. |
| 11. Downstream Flows | Moderate | Dewatered zone impacts small scale 3 solar lift irrigation systems, mills, and flow release. |
| 12. Climate Change & Hazards | Moderate | Seismic risk considerations, dynamic river flows, and required GLOF updates. |

# KEY E&S OBSERVATIONS & GAP ANALYSIS

A. Positive E&S Features

- Zero Physical Displacement: No household relocation or physical displacement is required, keeping social disruption low.

- Minimal Upstream Vulnerability: There are no residential settlements upstream of the reservoir impoundment zone.

- Low Forest & Flora Impact: Only 225 trees to be cleared across 49 ha of degraded forest land, resulting in low net forestry loss. No community forest land is impacted.

- Fish and Biodiversity Protection: To ensure habitat connectivity for migratory species like Snow Trout and Copper Mahseer, the project envisages fish elevators and passages.

- Watershed Protection: A dedicated Catchment Area Treatment (CAT) Plan and Reservoir Rim Treatment Plan are proposed to manage erosion and maintain soil stability, ensuring the long-term health of the river system

- Minimal Direct GLOF Risk: Glacial lakes were identified 150 km upstream from the headworks. Studies indicate low vulnerability to direct Glacial Lake Outburst Floods (GLOF).

- High Social Support: Public consultations (214 participants across 21 Sept 2013 hearings) showed 97% community willingness to support the project.

- Dedicated Implementation Structure: The Proponent commits to an Environmental and Social Management Unit (ESMU), an E&S Implementation Unit (ESIU), and independent Third-Party Monitoring.

- Economic Empowerment: The project has communicated clear, tangible benefits, including:

  - Priority Local Employment: Anticipating a peak workforce of 1,200 workers, the project prioritizes local hiring and pre-construction skill enhancement.

  - Infrastructure Support: Commitments include establishing higher secondary schools, drinking water systems, and improving local health clinics.

B. E&S Opportunities

The project identifies several technical areas as strategic opportunities to align with modern international lender standards (such as the IFC Performance Standards).

- Upgrading Regulatory Frameworks: While the original EIA was based on the 1997 framework, the project is currently undergoing a revised EIA to meet the latest national regulatory requirements and Good Industry International Practices.

- Advanced Climate Resilience: The project recognizes that updated GLOF and climate-change assessments are opportunities to implement engineering resilience, protecting the asset from long-term hydrological shifts.

- Optimized Resource Management: The generation of ~719,000 m³ of muck is proposed to be managed through a Muck Disposal Plan that includes bioengineering, afforestation, and the creation of greenbelts at disposal sites, turning construction byproducts into environmental assets.

- Sustainable Water Use: To balance energy production with downstream needs, the project plans to release a dedicated environmental flow of 2.03 m³/s. This flow ensures that traditional water mills, irrigation canals, and cremation sites remain fully functional.

C. Governance and Monitoring Framework

- Project Management Unit (PMU): Handles local stakeholder facilitation, public grievances, CSR programs, and the Land Acquisition & Compensation Facilitation Committee (LACFC).

- Environmental & Social Management Unit (ESMU):

  - ESIU Subunit (Implementation): Oversees non-contractor community/CSR activities in coordination with local NGO/INGO partners.

  - ESMU Subunit (Monitoring): Oversees site supervision via the Supervision Consultant and prepares quarterly monitoring reports.

- Third-Party External Monitor: Conducts independent compliance audits via a dedicated consulting contract starting 6 months prior to civil works.

# MITIGATION STRATEGY & ENVIRONMENTAL MANAGEMENT PLAN (EMP)

The proponent's management framework outlines specific mitigation plans that must be enforced via tender and contract documents:

| Focus Area | Proposed EMP & Mitigation Action Plans |
| --- | --- |
| Catchment & Slope Stability | Bioengineering, River Training Works, Catchment Area Treatment (CAT) Plan, Disaster Management Plan (DRM Plan). |
| Spoil & Erosion Management | Spoil Disposal Site Restoration (36 ha), sedimentation tanks at BPCP, water sprinkling for dust control. |
| Water & Downstream Protection | Wastewater treatment prior to river release, operational water release for 3 solar lift irrigation schemes. |
| Aquatic & Terrestrial Biodiversity | Fish Management Plan, Fish Elevator installation, Biodiversity & Wildlife Conservation Management Plan, Terrestrial Ecology, Habitat Protection, Restoration and Management Plan |
| Social & Livelihood Restoration | LACFC Compensation, Vulnerable Community Development Plan (VCDP) for Dalits, reinstatement of suspension bridge & fishpond. |

Specific Mitigation Commitments in EIA

- Social & Community Infrastructure: Establish a Land Acquisition & Compensation Facilitation Committee (LACFC) chaired by the Chief District Officer (CDO). Implement a dedicated Vulnerable Community Development Plan (VCDP) for Dalit groups, support local pre-construction skill training, provide local employment, and reinstate damaged infrastructure.

- Blasting & Nuisance Controls: Avoid nighttime surface blasting. Conduct pre-construction structural baseline surveys of nearby residential structures, with guaranteed compensation for vibration-induced damage.

- Worker Accommodation & Health: Enforce strict camp standards, a total prohibition on open defecation, wastewater treatment plants, and community health protection programs proposed.

- EMP Cost Allocation: The EMP budget is currently allocated at 0.86% of total project cost. Developers shall evaluate whether this allocation is adequate for all proposed structural and non-structural interventions and implementation of management plans.

# RECOMMENDED ACTION ITEMS & ACTION PLAN

To ensure alignment with international standards (IFC Performance Standards, Equator Principles) and manage credit risk, these are the initial recommended action items:

- Revised EIA & Gap Assessments: Ensure the updated EIA complies with Nepal's EPA 2019/EPR 2020 and IFC Performance Standards, including updated study on climate change and GLOF.  Ensure the implementation of management plans and mitigation measures identified through revised EIA.

- Engineering Alignment for fish elevator: Immediate incorporation of the fish elevator into the final approved structural and civil engineering drawings or as suggested by revised EIA.

- Downstream Water & Asset Reinstatement Plan: Finalize operational rules guaranteeing sufficient E-flow for the 3 solar lift irrigations, stone mills, and cremation sites. Covenant the proponent to rebuild the suspension bridge and private fishpond.

- Temple Relocation & Highway Inundation Mitigation: Finalize civil works plans for raising vulnerable highway sections and executing the physical relocation of the highway temple & suspension bridge with local consensus.

- Integration of E&S into Tender/Bidding Documents: Enforce strict EHS, labor camp, and spoil management covenants directly into the EPC and contractor tender documents.

- EMP Budget Audit: Request an independent cost review to verify if the 0.86% EMP allocation is sufficient to implement all required management plans.

**This action plan is subject to changes following final Hydroselect Recommendation and Revised EIA Mitigation Measures.

# CONCLUSION

In conclusion, the Tila-1 Hydropower Project presents a favorable fundamental E&S profile, highlighted by zero physical resettlement, strong local community acceptance (97%), and minimal baseline forest clearing. However, several critical compliance and engineering gaps, most notably the outdated 1997 legislative baseline, missing fish elevator details in civil designs, downstream water dependencies (solar lift systems and mills), and the potential under-budgeting of the EMP (at 0.86%) must be systematically addressed. Provided the developer commits to updating the EIA to current legal standards (EPA 2019 / EPR 2020), integrating explicit E&S provisions into contractor tender documents, and fulfilling all proposed structural reinstatements, the environmental and social risks remain well within acceptable parameters for bank financing.